## Sheet1
Company | Component Status | Created on | ID | Its Operations are Planned | Last Updated on | Priority | Product | Quantity To Produce | Product Unit of Measure | Reference | Source | Start | End | State | Deadline | Components/Product | Components/Product/ID | Components/Quantity To Consume | Work Orders/Work Center | Work Orders/Work Center/ID | Work Orders/Expected Duration | Work Orders/Subcontract Wo
TBRM Machining B.V. | Available | 2025-03-27 13:33 | __export__.mrp_production_3837_9d0480b5 | TRUE | 2025-09-11 12:56 | Normal | [4022-666-65702(R1)] LSPH coverplate stud block | 1000 | Pcs | TBRM /MO/00328-002 | OP/14121 | 2024-12-18 01:00 | 2025-11-24 14:29 | In Progress | 2025-01-15 12:00 | [5601-0000-0009] ALU 6082 T6 vk 50 | __export__.product_product_14151_f981158c | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 1015 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 13090 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 5090 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 1000 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 1000 | FALSE
TBRM Machining B.V. | Available | 2024-12-06 10:20 | __export__.mrp_production_1064_688e92e1 | FALSE | 2025-03-19 14:39 | Normal | [7005-2480-0090] METROFRAME BODY V02-00-B / 0119073001 | 4 | Pcs | TBRM /MO/00305 | S02403 | 2025-02-07 01:00 | 2025-02-28 01:00 | Confirmed | 2025-02-28 01:00 | [5601-0000-0155] ALU 5083 gegoten gzgd plaat 590x460x150 | __export__.product_product_16215_287d75f5 | 0 | M3-02 - Accuwell - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | 1530 | FALSE
[19 empty] | M5-04 - Haas - 5axis - Manual (UMC750SS) | __export__.mrp_workcenter_62_468a38e5 | 2860 | FALSE
TBRM Machining B.V. | Available | 2025-02-11 17:09 | __export__.mrp_production_1927_52ea08e3 | TRUE | 2025-02-25 09:21 | Normal | [4022-671-49051] Bpam cover | 66 | Pcs | TBRM /MO/00323-003 | Manual Replenishment | 2025-02-25 09:21 | 2025-02-28 09:15 | Confirmed | 2025-01-17 09:44 | [5601-0000-0018] ALU 6082 gzgd plaat 120x110x20 | __export__.product_product_14160_dc40221b | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 66 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 66 | FALSE
[19 empty] | M3-02 - Accuwell - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | 948 | FALSE
[19 empty] | M3-02 - Accuwell - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | 288 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 66 | FALSE
TBRM Machining B.V. | Available | 2024-12-18 12:47 | __export__.mrp_production_1104_d3ae4426 | TRUE | 2025-02-24 14:57 | Normal | [4022-651-55002A] Gpas preamp CB Box + cover assy | 27 | Pcs | TBRM /MO/00333 |  | 2025-02-28 11:31 | 2025-03-10 10:13 | Confirmed |  | [5602-0000-0023] RVS 316L wgw vk 80 | __export__.product_product_14190_b2f6cfa7 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 42 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 1710 | FALSE
[19 empty] | M5-02 - Accuwell - 5axis - Conveyor automation (FR5_02) | __export__.mrp_workcenter_58_a525d5b9 | 1035 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 108 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 27 | FALSE
TBRM Machining B.V. | Available | 2025-02-13 14:52 | __export__.mrp_production_1936_a4c4d921 | TRUE | 2025-02-26 11:37 | Normal | [4022-333-11506] lagerblok | 300 | Pcs | TBRM /MO/00422 |  | 2025-03-19 13:20 | 2025-09-09 09:17 | Confirmed | 2025-03-26 14:00 | [5602-0000-0041] RVS 430F blank rond 50h9 | __export__.product_product_15120_10aecd71 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 315 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 390 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 6390 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 1590 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 600 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 300 | FALSE
TBRM Machining B.V. |  | 2025-04-09 11:52 | __export__.mrp_production_3892_cec21dc3 | FALSE | 2025-04-09 11:52 | Normal | [7351522] Impact cover-6_rev-0 alleen base voor export-AP214.step | 1 | Pcs | TBRM /MO/00620 | S02910 | 2025-03-31 02:00 | 2025-04-14 02:00 | Draft | 2025-04-14 02:00
TBRM Machining B.V. | Available | 2025-08-28 10:59 | __export__.mrp_production_4738_6a3434f8 | FALSE | 2025-08-28 11:05 | Normal | [1508130 B] [Q] excenter housing z | 140 | Pcs | TBRM /MO/00710-002 | Manual Replenishment | 2025-04-23 02:00 | 2025-05-14 02:00 | Confirmed | 2025-05-14 13:28 | [5601-0000-0012] ALU 6082 T6 plat 60x40 | __export__.product_product_14154_75692b32 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 155 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 7090 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 790 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 700 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 140 | FALSE
TBRM Machining B.V. | Available | 2025-04-24 10:59 | __export__.mrp_production_4220_edb0630a | FALSE | 2025-06-03 09:13 | Normal | [349520-8007-000-0107] BYPASS (BLOK) | 89 | Pcs | TBRM /MO/00646 | S02965 | 2025-05-06 02:00 | 2025-05-27 02:00 | In Progress | 2025-05-27 09:27 | [5602-0000-0012] RVS 304/304L wgw vk 60 | __export__.product_product_14179_b017bfd8 | 6290 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 104 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 4540 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 535 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 445 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 89 | FALSE
TBRM Machining B.V. | Available | 2024-12-06 10:20 | __export__.mrp_production_1065_d70e7a5a | FALSE | 2025-03-19 14:39 | Normal | [7005-2480-0090] METROFRAME BODY V02-00-B / 0119073001 | 4 | Pcs | TBRM /MO/00306 | S02403 | 2025-05-09 02:00 | 2025-05-30 02:00 | Confirmed | 2025-05-30 02:00 | [5601-0000-0155] ALU 5083 gegoten gzgd plaat 590x460x150 | __export__.product_product_16215_287d75f5 | 0 | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 1530 | FALSE
[19 empty] | M5-04 - Haas - 5axis - Manual (UMC750SS) | __export__.mrp_workcenter_62_468a38e5 | 2860 | FALSE
TBRM Machining B.V. | Available | 2025-06-11 10:29 | __export__.mrp_production_4371_a96fc1a8 | FALSE | 2025-07-07 09:49 | Normal | [216121-0006] fixing block, actuator | 10 | Pcs | TBRM /MO/00746 | S03183 | 2025-05-23 02:00 | 2025-07-11 02:00 | Confirmed | 2025-07-09 02:00 | [5602-0000-0037] RVS 304/304L wgw plat 25x20 | __export__.product_product_15116_26d7d7fd | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 25 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 90 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 10 | FALSE
TBRM Machining B.V. | Available | 2025-05-20 13:51 | __export__.mrp_production_4331_24679a18 | TRUE | 2025-05-28 14:55 | Normal | [4022-656-73531] Pipe clamp exhaust FW 1980 | 86 | Pcs | TBRM /MO/00718 | OP/14069 - S03115 | 2025-06-05 08:00 | 2025-06-20 11:29 | Confirmed | 2025-06-26 02:00 | [5602-0000-0013] RVS 304/304L blank plat 50x8 | __export__.product_product_14180_b574d432 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 101 | FALSE
[19 empty] | M4-02 - Accuwell - 4axis - Conveyor automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | 434 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 172 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 86 | FALSE
TBRM Machining B.V. | Available | 2025-06-11 10:29 | __export__.mrp_production_4372_507a54db | FALSE | 2025-07-03 09:44 | Normal | [216121-0007] YS gripper detect mirro block | 71 | Pcs | TBRM /MO/00747 | S03183 | 2025-06-13 02:00 | 2025-07-04 02:00 | Confirmed | 2025-07-09 02:00 | [5602-0000-0015] RVS 304/304L wgw plat 80x30 | __export__.product_product_14182_446dd894 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 86 | FALSE
[19 empty] | M5-02 - Accuwell - 5axis - Conveyor automation (FR5_02) | __export__.mrp_workcenter_58_a525d5b9 | 1297 | FALSE
[19 empty] | M5-02 - Accuwell - 5axis - Conveyor automation (FR5_02) | __export__.mrp_workcenter_58_a525d5b9 | 445 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 213 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 71 | FALSE
TBRM Machining B.V. | Available | 2025-05-13 10:47 | __export__.mrp_production_4315_9685bbb0 | FALSE | 2025-07-07 10:05 | Normal | [4022-637-24142] HINGE BLOCK FIXED RF | 44 | Pcs | TBRM /MO/00706 | S03084 | 2025-06-20 02:00 | 2025-07-11 02:00 | Confirmed | 2025-07-11 02:00 | [5602-0000-0003] RVS 304/304L wgw plat 40x30 | __export__.product_product_14170_ab4f36b5 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 59 | FALSE
[19 empty] | M5-02 - Accuwell - 5axis - Conveyor automation (FR5_02) | __export__.mrp_workcenter_58_a525d5b9 | 1410 | FALSE
[19 empty] | M4-02 - Accuwell - 4axis - Conveyor automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | 530 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 132 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 44 | FALSE
TBRM Machining B.V. | Available | 2025-06-03 08:53 | __export__.mrp_production_4353_d89b44b5 | FALSE | 2025-07-17 09:39 | Normal | [349520-8007-000-0107] BYPASS (BLOK) | 187 | Pcs | TBRM /MO/00733 | S03154 | 2025-07-03 02:00 | 2025-07-24 02:00 | Confirmed | 2025-07-24 02:00 | [5602-0000-0012] RVS 304/304L wgw vk 60 | __export__.product_product_14179_b017bfd8 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 202 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 9440 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 1025 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 935 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 187 | FALSE
TBRM Machining B.V. |  | 2025-07-16 10:13 | __export__.mrp_production_4488_2c73b7e5 | FALSE | 2025-07-16 10:13 | Normal | [4022-656-74553] Assy support guide FW 1980 | 50 | Pcs | TBRM /MO/00833 | OP/14070 - S03325 | 2025-07-07 02:00 | 2025-07-28 02:00 | Draft | 2025-07-28 02:00 |  |  |  | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 50 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 1340 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 100 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 50 | FALSE
TBRM Machining B.V. | Available | 2025-01-29 08:14 | __export__.mrp_production_1197_849443cd | TRUE | 2025-02-25 09:29 | Normal | [1082700B] Block cooling water TMP | 68 | Pcs | TBRM /MO/00390 |  | 2025-07-17 14:51 | 2025-07-29 10:37 | Confirmed |  | [5602-0000-0024] RVS 316L wgw plat 40x25 | __export__.product_product_14191_eab5834c | 0 | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 2538 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 430 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 340 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 68 | FALSE
TBRM Machining B.V. | Available | 2025-07-23 11:14 | __export__.mrp_production_4537_9e9f5b4c | TRUE | 2025-09-08 09:14 | Normal | [00385-00-321-A] Plint fixing strip left | 189 | Pcs | TBRM /MO/00847 | Manual Replenishment | 2025-07-23 02:00 | 2025-11-14 09:39 | Confirmed | 2025-08-20 11:14 | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 204 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 1602 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 846 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 378 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 189 | FALSE
TBRM Machining B.V. | Not Available | 2025-07-23 11:14 | __export__.mrp_production_4538_1037cce1 | TRUE | 2025-09-08 09:14 | Normal | [00385-00-346-A] Plint fixing strip right | 501 | Pcs | TBRM /MO/00848 | Manual Replenishment | 2025-07-23 02:00 | 2025-10-17 11:39 | Confirmed | 2025-08-20 11:14 | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 516 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 4098 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 2094 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 1002 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 501 | FALSE
TBRM Machining B.V. | Available | 2025-06-11 10:29 | __export__.mrp_production_4370_ea015248 | FALSE | 2025-09-03 14:04 | Normal | [216121-0005] base wet stem quatro | 49 | Pcs | TBRM /MO/00745 | S03183 | 2025-08-01 02:00 | 2025-09-19 02:00 | In Progress | 2025-09-19 02:00 | [5601-0000-0107] ALU 5754 H111 gzgd plaat 60x50x50 | __export__.product_product_15090_ae4a700a | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 0 | FALSE
[19 empty] | M5-01 - Accuwell - 5axis - Pallet automaton (FR5_01) | __export__.mrp_workcenter_59_d6deab7b | 1315 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 384 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 286 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 392 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 245 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 49 | FALSE
TBRM Machining B.V. | Exp 04/09/2025 | 2025-08-22 09:49 | __export__.mrp_production_4694_32ee4fbd | FALSE | 2025-09-05 14:52 | Normal | [P1538-M9011-01] Probe Holder TYPE AA | 2 | Pcs | TBRM /MO/00904 | S03419 | 2025-08-01 02:00 | 2025-08-22 02:00 | Confirmed | 2025-08-22 02:00 | [5601-0000-0188] ALU 5083 gegoten 6z gezaagd 75x30 | __export__.product_product_17989_ba0534bc | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 135 | FALSE
TBRM Machining B.V. | Available | 2025-08-22 09:49 | __export__.mrp_production_4695_6a7cbaf5 | TRUE | 2025-09-15 11:27 | Normal | [P1538-M9010-00] Base_Plate | 2 | Pcs | TBRM /MO/00905 | S03419 | 2025-08-01 02:00 | 2025-09-23 13:54 | In Progress | 2025-08-22 02:00 | [5601-0000-0189] ALU 5083 gegoten 6z gezaagd 100x30 | __export__.product_product_17990_28ad82dc | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 135 | FALSE
[19 empty] | M5-04 - Haas - 5axis - Manual (UMC750SS) | __export__.mrp_workcenter_62_468a38e5 | 258 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
TBRM Machining B.V. | Exp 04/09/2025 | 2025-09-10 16:15 | __export__.mrp_production_4883_59addbd3 | FALSE | 2025-09-11 11:19 | Normal | [P1538-M9011-01] Probe Holder TYPE AA | 2 | Pcs | TBRM /MO/00993 | S03419 | 2025-08-01 02:00 | 2025-08-22 02:00 | Confirmed | 2025-08-22 02:00 | [5601-0000-0188] ALU 5083 gegoten 6z gezaagd 75x30 | __export__.product_product_17989_ba0534bc | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 135 | FALSE
TBRM Machining B.V. | Available | 2025-09-10 16:15 | __export__.mrp_production_4884_df54157f | FALSE | 2025-09-15 09:04 | Normal | [P1538-M9010-00] Base_Plate | 2 | Pcs | TBRM /MO/00994 | S03419 | 2025-08-01 02:00 | 2025-08-22 02:00 | Confirmed | 2025-08-22 02:00 | [5601-0000-0189] ALU 5083 gegoten 6z gezaagd 100x30 | __export__.product_product_17990_28ad82dc | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 135 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 258 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
TBRM Machining B.V. | Available | 2025-07-25 09:39 | __export__.mrp_production_4542_91f6e67f | TRUE | 2025-08-27 09:24 | Normal | [4022-635-87282] LOCKING PLATE | 428 | Pcs | TBRM /MO/00850 | OP/14059 - S03362 | 2025-08-07 02:00 | 2025-12-12 08:35 | In Progress | 2025-09-05 13:00 | [5603-0000-0008] STAAL S235JRC+C blank plat 25x20 | __export__.product_product_14203_67d906dd | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 443 | FALSE
[19 empty] | M5-02 - Accuwell - 5axis - Conveyor automation (FR5_02) | __export__.mrp_workcenter_58_a525d5b9 | 1802 | FALSE
[19 empty] | M3-02 - Accuwell - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | 518 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 428 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 1284 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 428 | FALSE
TBRM Machining B.V. | Available | 2025-08-08 12:54 | __export__.mrp_production_4593_b4e857db | FALSE | 2025-09-09 08:58 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 761 | Pcs | TBRM /MO/00878 |  | 2025-08-08 12:54 | 2025-09-26 12:54 | Confirmed |  | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 776 | FALSE
[19 empty] | M4-02 - Accuwell - 4axis - Conveyor automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | 19115 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 3134 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 2283 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 9000 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 761 | FALSE
TBRM Machining B.V. | Available | 2025-07-21 15:32 | __export__.mrp_production_4501_d08a63ff | TRUE | 2025-07-23 12:42 | Normal | [4022.666.20971-TBRM MCH] WTP IM MK6 BRACKET RING | 500 | Pcs | TBRM /MO/00844 | S03339 | 2025-08-12 02:00 | 2025-09-17 13:10 | Confirmed | 2025-09-02 02:00 | [4022.666.20971ABLaserfileV2] WTP IM MK6 BRACKET RING laser cutted + laser marking blank / 4022.666.20971ABLaserfileV2 | __export__.product_product_17402_254f1ca1 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 500 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 11660 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-09-02 09:35 | __export__.mrp_production_4808_a7f1fb7f | FALSE | 2025-09-11 11:39 | Normal | [4022.644.9779] NXE NH Gripper LVL Tool Cover | 1 | Pcs | TBRM /MO/00950 | Manual Replenishment | 2025-08-12 02:00 | 2025-09-02 02:00 | Confirmed | 2025-09-02 09:34 | [5601-0000-0104] ALU 6082 T651 (wgw) gzgd plaat 255x225x8 | __export__.product_product_14712_cb29254c | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 1 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 222 | FALSE
TBRM Machining B.V. | Available | 2025-08-14 09:43 | __export__.mrp_production_4654_d6430928 | FALSE | 2025-08-26 14:04 | Normal | [4022.622.61761] RH RED EBOX MONO | 1 | Pcs | TBRM /MO/00886 | S03415 | 2025-08-14 02:00 | 2025-09-04 02:00 | Confirmed | 2025-09-04 02:00 | [5601-0000-0162] ALU 6082 T651 (wgw) gzgd plaat 240x180x150 | __export__.product_product_16324_074c9bd6 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 1 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 376 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | CMM - Hexagon - CMM (TIGO SF) | __export__.mrp_workcenter_69_1bd4f659 | 90 | FALSE
TBRM Machining B.V. | Available | 2025-09-01 11:42 | __export__.mrp_production_4751_66f93fbe | TRUE | 2025-09-15 11:52 | Normal | [7005-2540-0007] C beam v01-03 / 07201507 - Drawing in RED (40 x 40 x 5mm, welded tube) | 16 | Pcs | TBRM /MO/00947 | S03402 | 2025-08-18 02:00 | 2025-10-23 13:49 | In Progress | 2025-09-08 02:00 | [5602-0000-0066] RVS1.4307 (304L) HF gelaste buis 40x40x5 | __export__.product_product_17868_74bb9865 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 31 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 476 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
TBRM Machining B.V. | Available | 2025-08-21 14:12 | __export__.mrp_production_4690_a8692658 | FALSE | 2025-08-28 09:20 | Normal | [00385-00-102-C] Height bearing clamp plate | 374 | Pcs | TBRM /MO/00900 | Manual Replenishment | 2025-08-21 02:00 | 2025-10-09 02:00 | Confirmed | 2025-10-09 14:12 | [5603-0000-0003] STAAL S355J2C+C ngl plat 50x20 | __export__.product_product_14198_828edea3 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 389 | FALSE
[19 empty] | M4-02 - Accuwell - 4axis - Conveyor automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | 3082 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 1212 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 9000 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 374 | FALSE
TBRM Machining B.V. | Available | 2025-06-23 12:18 | __export__.mrp_production_4431_8f774222 | FALSE | 2025-09-08 14:18 | Normal | [4022.689.94931] RH RED DP PT LOWER COVER | 1 | Pcs | TBRM /MO/00780 | S03241 | 2025-08-22 02:00 | 2025-09-12 02:00 | Confirmed | 2025-09-12 02:00 | [5601-0000-0182] ALU 5083 (O3) gegoten 6z gezaagd plaat 570x350x50 | __export__.product_product_17605_d1ef1d9f | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 60 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 304 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-06-23 12:18 | __export__.mrp_production_4432_1b0065fa | FALSE | 2025-09-11 11:38 | Normal | [4022.689.94981] RH RED DP PT UPPER COVER | 1 | Pcs | TBRM /MO/00781 | S03241 | 2025-08-22 02:00 | 2025-09-12 02:00 | Confirmed | 2025-09-12 02:00 | [5601-0000-0181] ALU 5083 (O3) gegoten 6z gezaagd plaat 610x350x30 | __export__.product_product_17604_d75bd19d | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 1 | FALSE
TBRM Machining B.V. | Not Available | 2025-09-03 11:59 | __export__.mrp_production_4841_95fde8df | FALSE | 2025-09-16 09:30 | Normal | [4522-980-37891] Filterplate al 5 | 201 | Pcs | TBRM /MO/00951 | S03474 | 2025-08-28 02:00 | 2025-09-18 02:00 | Confirmed | 2025-09-18 11:00 | [5601-0000-0118] ALU 99.5 40HV UN-T136 plaat 145x145x6 | __export__.product_product_15101_5dce5b8d | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 0 | FALSE
[19 empty] | M3-02 - Accuwell - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | 1698 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 201 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 201 | FALSE
TBRM Machining B.V. | Available | 2025-09-09 11:20 | __export__.mrp_production_4876_25524b57 | FALSE | 2025-09-11 12:27 | Normal | [S325F3116200B] Bracket | 1 | Pcs | TBRM /MO/00986 | S03489 | 2025-08-29 02:00 | 2025-09-19 02:00 | Confirmed | 2025-09-19 11:00 | [5601-0000-0105] ALU 2024-T351 gecert. 110x15x10 | __export__.product_product_15088_16503d30 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 0 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 98 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 92 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 1 | FALSE
TBRM Machining B.V. | Available | 2025-09-11 09:34 | __export__.mrp_production_4891_fadea379 | FALSE | 2025-09-15 15:12 | Normal | [1011113A] Cord Bracket | 134 | Pcs | TBRM /MO/00998 | OP/14046 - S03504 | 2025-08-29 02:00 | 2025-09-19 02:00 | Confirmed | 2025-09-19 02:00 | [5604-0000-0002] MESSING CuZn40Pb2 plat 30x20 | __export__.product_product_14165_af7aab6e | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 149 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 760 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 358 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 268 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 134 | FALSE
TBRM Machining B.V. | Available | 2025-07-25 09:56 | __export__.mrp_production_4543_067bdfa8 | TRUE | 2025-09-03 13:13 | Normal | [BD50-5085-011-C] bracket | 50 | Pcs | TBRM /MO/00851 | S03364 | 2025-09-03 02:00 | 2026-01-21 16:09 | In Progress | 2025-10-08 02:00 | [5601-0000-0021] ALU 7075 T79511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 50 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 390 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 100 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 50 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 50 | FALSE
TBRM Machining B.V. | Available | 2025-09-10 10:01 | __export__.mrp_production_4878_21ea97fa | FALSE | 2025-09-15 13:23 | Normal | [7384477] 4023 006 59361-A-Mountblock left.stp | 1 | Pcs | TBRM /MO/00988 | S03498 | 2025-09-03 02:00 | 2025-09-17 02:00 | Confirmed | 2025-09-17 02:00 | [5605-0000-0012] POM-C zwart gzgd plaat 100x30 | __export__.product_product_14466_8c617159 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 16 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 74 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 74 | FALSE
TBRM Machining B.V. | Exp 21/08/2025 | 2025-09-10 10:01 | __export__.mrp_production_4879_80fcca25 | FALSE | 2025-09-15 11:19 | Normal | [7385699] 4023 006 59351-A-Mountblock right.stp | 1 | Pcs | TBRM /MO/00989 | S03498 | 2025-09-03 02:00 | 2025-09-17 02:00 | Confirmed | 2025-09-17 02:00 | [5605-0000-0013] POM-C zwart gzgd plaat 150x30 | __export__.product_product_14467_e8bbb011 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 16 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 83 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 74 | FALSE
TBRM Machining B.V. | Available | 2025-08-26 13:24 | __export__.mrp_production_4732_81664447 | FALSE | 2025-09-01 16:14 | Normal | [4022-666-18121] Distance Bush 1 | 342 | Pcs | TBRM /MO/00940 | OP/14074 - S03452 | 2025-09-04 02:00 | 2025-09-25 02:00 | Confirmed | 2025-09-25 02:00 | [5602-0000-0017] RVS 304/304L blank vk 10 | __export__.product_product_14184_848b2c42 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 357 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 3168 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 684 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 342 | FALSE
TBRM Machining B.V. | Exp 15/09/2025 | 2025-06-20 14:37 | __export__.mrp_production_4415_77534b29 | FALSE | 2025-09-08 14:10 | Normal | [4022.684.31521] RH RED RZ BRAKE HOUSING | 3 | Pcs | TBRM /MO/00776 | S03237 | 2025-09-05 02:00 | 2025-09-26 02:00 | Confirmed | 2025-09-26 02:00 | [5602-0000-0063] RVS 316L custom blank for 4022.684.315212VN / 31521AA stock | __export__.product_product_17542_b05df8a1 | 0 | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 330 | FALSE
TBRM Machining B.V. | Available | 2025-08-21 14:46 | __export__.mrp_production_4693_50d028d9 | FALSE | 2025-09-08 15:19 | Normal | [RRDE.CAP] Teflon lid for the RRDE cell / Metrohm / P1439-M0105-04 | 50 | Pcs | TBRM /MO/00903 | S03438 | 2025-09-05 02:00 | 2025-09-26 02:00 | Confirmed | 2025-09-26 02:00 | [5606-0000-0004] PTFE gzgd plaat 500x225x30 | __export__.product_product_17986_29e78a81 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 50 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 1160 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 460 | FALSE
TBRM Machining B.V. | Available | 2025-09-09 10:48 | __export__.mrp_production_4875_38ec7d1f | FALSE | 2025-09-09 10:48 | Normal | [4022.622.61092] RH RED GRIPPER CABLE COVER | 40 | Pcs | TBRM /MO/00985 | S03487 | 2025-09-08 02:00 | 2025-11-03 01:00 | Confirmed | 2025-11-03 01:00 | [5602-0000-0031] RVS 316L wgw plat 80x20 | __export__.product_product_14485_407ff3ad | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 55 | FALSE
[19 empty] | M5-04 - Haas - 5axis - Manual (UMC750SS) | __export__.mrp_workcenter_62_468a38e5 | 860 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 1340 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 6750 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 40 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4851_6338f774 | FALSE | 2025-09-09 12:57 | Normal | Frameplate top new / VDM / P01830 | 2 | Pcs | TBRM /MO/00962 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0028] ALU 6082 T651 (wgw) gzgd plaat 200x30 | __export__.product_product_14384_d92cbc88 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 17 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 146 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 170 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4852_5e07b84d | FALSE | 2025-09-09 17:08 | Normal | Motor plate / VDM / P01814 | 2 | Pcs | TBRM /MO/00963 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0192] ALU 6082 T651 (wgw) gzgd plaat 465x250x30 | __export__.product_product_18072_2a47d3d4 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 2 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 292 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4853_7ee9a8ec | FALSE | 2025-09-11 08:10 | Normal | Frameplate left new / VDM / P01829 | 2 | Pcs | TBRM /MO/00964 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0028] ALU 6082 T651 (wgw) gzgd plaat 200x30 | __export__.product_product_14384_d92cbc88 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 17 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 150 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 114 | FALSE
TBRM Machining B.V. | Available | 2025-09-03 17:30 | __export__.mrp_production_4854_21c64061 | FALSE | 2025-09-09 17:12 | Normal | Frameplate chopcot plate / VDM / P01815 | 3 | Pcs | TBRM /MO/00965 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0026] ALU 6082 T651 (wgw) gzgd plaat 150x30 | __export__.product_product_14382_ec76d96c | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 18 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 240 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4855_05b1548f | FALSE | 2025-09-11 08:10 | Normal | Frameplate right new / VDM / P01827A | 1 | Pcs | TBRM /MO/00966 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0028] ALU 6082 T651 (wgw) gzgd plaat 200x30 | __export__.product_product_14384_d92cbc88 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 16 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 99 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 96 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4856_212c5134 | FALSE | 2025-09-09 17:04 | Normal | Frame plate / VDM / P01813 | 1 | Pcs | TBRM /MO/00967 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0191] ALU 6082 T651 (wgw) gzgd plaat 430x275x30 | __export__.product_product_18070_329af9d4 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 1 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 135 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 137 | FALSE
TBRM Machining B.V. | Available | 2025-09-03 17:30 | __export__.mrp_production_4857_4ade3b7f | FALSE | 2025-09-09 12:15 | Normal | Support Bar DTC6 / VDM / P01817 | 2 | Pcs | TBRM /MO/00968 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0023] ALU 6082 T651 (wgw) gzgd plaat 75x30 | __export__.product_product_14379_b8846587 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 17 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 102 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 144 | FALSE
TBRM Machining B.V. | Exp 16/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4858_fa5e5df9 | FALSE | 2025-09-09 12:30 | Normal | Frameplate chopcot outer plate 6 holes / VDM / P01826 | 3 | Pcs | TBRM /MO/00969 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0190] ALU 6082 T651 (wgw) gzgd plaat 500x250x30 | __export__.product_product_18066_0a832a0c | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 3 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 582 | FALSE
TBRM Machining B.V. | Available | 2025-09-03 17:30 | __export__.mrp_production_4859_ec205d90 | FALSE | 2025-09-16 09:15 | Normal | Dancer fixation plate #1 / VDM / P01868 | 1 | Pcs | TBRM /MO/00970 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0026] ALU 6082 T651 (wgw) gzgd plaat 150x30 | __export__.product_product_14382_ec76d96c | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 16 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 93 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 101 | FALSE
TBRM Machining B.V. | Exp 23/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4861_6f92590b | FALSE | 2025-09-15 16:04 | Normal | Vertical bobbin brake top plate / VDM / P03105 | 5 | Pcs | TBRM /MO/00972 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0193] ALU 6082 T651 (wgw) gzgd plaat 280x275x30 | __export__.product_product_18091_3d87dd1c | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 5 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 195 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 220 | FALSE
TBRM Machining B.V. | Exp 23/09/2025 | 2025-09-03 17:30 | __export__.mrp_production_4862_7676af0b | FALSE | 2025-09-15 16:14 | Normal | Vertical bobbin brake bottom plate / VDM / P03106 | 5 | Pcs | TBRM /MO/00973 | S03476 | 2025-09-09 02:00 | 2025-09-30 02:00 | Confirmed | 2025-09-30 02:00 | [5601-0000-0195] ALU 6082 T651 (wgw) gzgd plaat 255x250x30 | __export__.product_product_18092_2c7a9ed8 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 5 | FALSE
TBRM Machining B.V. | Available | 2025-07-29 11:40 | __export__.mrp_production_4569_f584dd85 | TRUE | 2025-07-29 11:42 | Normal | [4022-333-58791] Filterhouder Cu 0.1 | 128 | Pcs | TBRM /MO/00859 | OP/14049 - S03378 | 2025-09-12 02:00 | 2025-09-16 13:18 | Confirmed | 2025-08-19 13:00 | [5604-0000-0005] MESSING CuZn40Pb3 plat 16x2 | __export__.product_product_15113_f0f788d6 | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 128 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 474 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 640 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 128 | FALSE
TBRM Machining B.V. | Available | 2025-08-12 13:03 | __export__.mrp_production_4647_f9f4acfc | FALSE | 2025-08-22 14:26 | Normal | [4022.632.63021] WTP LOCKING NUT | 1700 | Pcs | TBRM /MO/00879 | S03410 | 2025-09-12 02:00 | 2025-10-03 02:00 | Confirmed | 2025-10-03 02:00 | [5602-0000-0058] RVS 303 (1.4305) wgw geschild rond dia 40 | __export__.product_product_17313_9cdb5eb7 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 1715 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 23010 | FALSE
TBRM Machining B.V. | Exp 18/09/2025 | 2025-09-12 12:43 | __export__.mrp_production_4894_c0252ff7 | FALSE | 2025-09-12 12:43 | Normal | [00429-00-662-B] Arret lever | 400 | Pcs | TBRM /MO/01000 | Manual Replenishment | 2025-09-12 02:00 | 2025-10-03 02:00 | Confirmed | 2025-10-03 12:43 | [5601-0000-0007] ALU 6082 T6 vk 30 | __export__.product_product_14149_55705e3a | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 415 | FALSE
[19 empty] | M4-02 - Accuwell - 4axis - Conveyor automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | 5690 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 800 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 400 | FALSE
TBRM Machining B.V. | Available | 2025-09-12 11:23 | __export__.mrp_production_4893_d2806c1c | FALSE | 2025-09-12 11:23 | Normal | [4022.704.19282] RH RED GRIPPER BODY | 14 | Pcs | TBRM /MO/00893-002 | S02820 | 2025-09-12 11:23 | 2025-10-03 11:23 | Confirmed |  | [5602-0000-0060] RVS 316/316L gzgd plaat 210x105x30 (tol. -0/+3mm) | __export__.product_product_17381_95528666 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 14 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 6780 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
TBRM Machining B.V. | Available | 2025-08-28 13:51 | __export__.mrp_production_4739_524a88c8 | FALSE | 2025-08-28 15:15 | Normal | [7001-2580-0016] Pusher Protect / FM / FM-02-012-B | 6 | Pcs | TBRM /MO/00944 | S03443 | 2025-09-15 02:00 | 2025-10-06 02:00 | Confirmed | 2025-10-06 02:00 | [5605-0000-0009] POM-C wit/naturel gzgd plaat 200x15 | __export__.product_product_14463_f928d0e0 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 21 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 138 | FALSE
TBRM Machining B.V. | Not Available | 2025-08-28 13:51 | __export__.mrp_production_4740_9f35f3cd | FALSE | 2025-08-28 15:16 | Normal | [7001-2580-0017] Pusher / FM / FM-02-011-B | 6 | Pcs | TBRM /MO/00945 | S03443 | 2025-09-15 02:00 | 2025-10-06 02:00 | Confirmed | 2025-10-06 02:00 | [5605-0000-0016] POM-C zwart gzgd plaat 150x50 | __export__.product_product_14470_eacf2e83 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 21 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 162 | FALSE
TBRM Machining B.V. | Available | 2025-08-26 13:22 | __export__.mrp_production_4731_76da22f3 | FALSE | 2025-08-26 13:22 | Normal | [4022-335-19371] Filterhouder Ni 0.02mm | 60 | Pcs | TBRM /MO/00939 | S03450 | 2025-09-16 02:00 | 2025-10-07 02:00 | Confirmed | 2025-10-07 02:00 | [5604-0000-0005] MESSING CuZn40Pb3 plat 16x2 | __export__.product_product_15113_f0f788d6 | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 60 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 270 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 300 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 61 | FALSE
TBRM Machining B.V. | Available | 2025-09-04 12:44 | __export__.mrp_production_4869_1b77fe36 | FALSE | 2025-09-15 16:38 | Normal | [00528-11649-A] air bearing duct holder / FME | 1 | Pcs | TBRM /MO/00980 | S03478 | 2025-09-17 02:00 | 2025-10-08 02:00 | Confirmed | 2025-10-08 02:00 | [5605-0000-0006] POM-C wit/naturel gzgd plaat 100x50 | __export__.product_product_14460_69202c49 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 16 | FALSE
[19 empty] | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 1 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 67 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 69 | FALSE
TBRM Machining B.V. | Available | 2025-09-04 12:44 | __export__.mrp_production_4870_41eb79f7 | FALSE | 2025-09-11 08:51 | Normal | [00528-11764-A] cover concave type 1 / FME | 1 | Pcs | TBRM /MO/00981 | S03478 | 2025-09-17 02:00 | 2025-10-08 02:00 | Confirmed | 2025-10-08 02:00 |  |  |  | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 87 | FALSE
TBRM Machining B.V. | Available | 2025-08-29 11:15 | __export__.mrp_production_4741_f9eb701f | FALSE | 2025-09-01 13:03 | Normal | [4022.644.9778] NXE LH Gripper LVLS Base | 2 | Pcs | TBRM /MO/00946 | S03460 | 2025-09-18 02:00 | 2025-10-09 02:00 | Confirmed | 2025-10-09 02:00 | [5601-0000-0036] ALU 6082 T651 (wgw) gzgd plaat 200x15 | __export__.product_product_14392_8b21e679 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 17 | FALSE
TBRM Machining B.V. | Available | 2025-08-19 09:38 | __export__.mrp_production_4683_3c974083 | TRUE | 2025-09-03 13:15 | Normal | [BD50-5075-009-E] bracket | 40 | Pcs | TBRM /MO/00895 | S03426 | 2025-09-19 02:00 | 2025-10-09 15:29 | In Progress | 2026-02-13 01:00 | [5601-0000-0021] ALU 7075 T79511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 40 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 250 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 80 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 40 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 40 | FALSE
TBRM Machining B.V. | Exp 17/09/2025 | 2025-09-05 14:27 | __export__.mrp_production_4873_a5eed2d5 | FALSE | 2025-09-11 08:39 | Normal | [7005-2580-0010] Cylinder bracket V01-00 / NFI / 27244703 | 8 | Pcs | TBRM /MO/00984 | S03484 | 2025-09-19 02:00 | 2025-10-10 02:00 | Confirmed | 2025-10-10 02:00 | [5601-0000-0176] ALU 5083 (O3) gegoten 6 zijdig gezaagd 295x250x30 | __export__.product_product_17009_eae1abf8 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 8 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 388 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
TBRM Machining B.V. | Available | 2025-07-23 10:33 | __export__.mrp_production_4536_e5dc26fa | FALSE | 2025-08-18 13:25 | Normal | [4022.704.19282] RH RED GRIPPER BODY | 30 | Pcs | TBRM /MO/00846 | S03357 | 2025-09-24 02:00 | 2025-10-15 02:00 | Confirmed | 2025-10-15 02:00 | [5602-0000-0060] RVS 316/316L gzgd plaat 210x105x30 (tol. -0/+3mm) | __export__.product_product_17381_95528666 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 30 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 14460 | FALSE
TBRM Machining B.V. | Available | 2025-08-19 09:41 | __export__.mrp_production_4684_d8802bab | FALSE | 2025-09-08 08:24 | Normal | [4022-680-5025] MBI WS MK2 F&T BMA CONNECT | 10 | Pcs | TBRM /MO/00896 | S03428 | 2025-09-26 02:00 | 2025-10-17 02:00 | Confirmed | 2025-10-17 02:00 | [5602-0000-0024] RVS 316L wgw plat 40x25 | __export__.product_product_14191_eab5834c | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 25 | FALSE
[19 empty] | M3-02 - Accuwell - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | 420 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
TBRM Machining B.V. | Available | 2025-08-19 09:43 | __export__.mrp_production_4685_7369251b | FALSE | 2025-09-09 12:54 | Normal | [4022-680-5023] MBI WS MK2 F&T BMA CONNECT 1 | 10 | Pcs | TBRM /MO/00897 | S03430 | 2025-09-26 02:00 | 2025-10-17 02:00 | Confirmed | 2025-10-17 02:00 | [5602-0000-0050] RVS 316L wgw plat 80x40 | __export__.product_product_16581_30702b4a | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 25 | FALSE
[19 empty] | M3-02 - Accuwell - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | 300 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4860_dddc055a | FALSE | 2025-09-03 17:30 | Normal | Dancer fixation plate #2 / VDM / P01869 | 1 | Pcs | TBRM /MO/00971 | S03476 | 2025-09-30 01:00 | 2025-09-30 02:00 | Draft | 2025-09-30 02:00
TBRM Machining B.V. |  | 2025-09-12 16:40 | __export__.mrp_production_4897_d1edef27 | FALSE | 2025-09-12 16:40 | Normal | [P1571-M1000-05] Cap for flat Cell / METROHM | 5 | Pcs | TBRM /MO/01001 | S03508 | 2025-09-30 01:00 | 2025-09-30 02:00 | Draft | 2025-09-30 02:00
TBRM Machining B.V. |  | 2025-09-12 16:40 | __export__.mrp_production_4898_23d86692 | FALSE | 2025-09-12 16:40 | Normal | [P1571-M1001-02] Plug / METROHM | 5 | Pcs | TBRM /MO/01002 | S03508 | 2025-09-30 01:00 | 2025-09-30 02:00 | Draft | 2025-09-30 02:00
TBRM Machining B.V. | Available | 2025-08-22 13:48 | __export__.mrp_production_4703_9eee2266 | FALSE | 2025-09-02 09:43 | Normal | [4022.699.1863] HALFFAB M TRANSP LCK VERT / HQ / 104011396 | 4 | Pcs | TBRM /MO/00911 | S03442 | 2025-09-30 02:00 | 2025-10-21 02:00 | Confirmed | 2025-10-21 02:00 | [5601-0000-0013] ALU 6082 T6 vk 60 | __export__.product_product_14155_0d2c4ba1 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 19 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 276 | FALSE
TBRM Machining B.V. | Exp 08/09/2025 | 2025-08-21 14:14 | __export__.mrp_production_4691_3c5f5e7b | FALSE | 2025-09-11 13:01 | Normal | [00385-00-113A] Tensioner plate | 712 | Pcs | TBRM /MO/00901 | Manual Replenishment | 2025-10-03 02:00 | 2025-10-31 01:00 | Confirmed | 2025-10-31 14:14 | [5990-0000-0018] Tensioner Plate cutout | __export__.product_product_15131_791d3010 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | 712 | FALSE
[19 empty] | M4-02 - Accuwell - 4axis - Conveyor automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | 10770 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 2136 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 712 | FALSE
TBRM Machining B.V. | Available | 2025-08-21 14:15 | __export__.mrp_production_4692_3ecd6c55 | FALSE | 2025-09-01 14:08 | Normal | [00385-00-320-A] Plint adjust strip | 633 | Pcs | TBRM /MO/00902 | Manual Replenishment | 2025-10-03 02:00 | 2025-10-31 01:00 | Confirmed | 2025-10-31 14:15 | [5603-0000-0005] STAAL S235JRC+C blank plat 40x10 | __export__.product_product_14200_70254936 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 648 | FALSE
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 3888 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 633 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 2250 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 633 | FALSE
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4704_415872a2 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0016] Pusher Protect / FM / FM-02-012-B | 3 | Pcs | TBRM /MO/00912 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4705_f8b0b68e | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0017] Pusher / FM / FM-02-011-B | 3 | Pcs | TBRM /MO/00913 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4706_63e7696a | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0018] Mountblock / FM / FM-02-013-B | 18 | Pcs | TBRM /MO/00914 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4707_c2d8357f | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0019] Monitor Support / FM / FM-02-046-B | 6 | Pcs | TBRM /MO/00915 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4708_7cdb1251 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0020] Monitor Support 2 / FM / FM-02-045-B | 6 | Pcs | TBRM /MO/00916 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4709_2da0f3c6 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0021] PARKING BLOCK / FM / FM-02-048-B | 3 | Pcs | TBRM /MO/00917 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4710_76215321 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0022] HOLDER CREDIT CARD / FM / FM-02-007-C | 3 | Pcs | TBRM /MO/00918 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4711_0cc474b4 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0023] TOP PLATE / FM / FM-02-003-C | 3 | Pcs | TBRM /MO/00919 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4712_b707d3ab | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0024] LIGHT L BRACKET / FM / FM-02-030-B | 3 | Pcs | TBRM /MO/00920 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4713_fb7fe3d2 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0025] Holder Lamp / FM / FM-02-037-B | 3 | Pcs | TBRM /MO/00921 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4714_8a363a61 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0026] Holder Fresnell / FM / FM-02-035-B | 3 | Pcs | TBRM /MO/00922 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4715_c1c16cea | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0027] Holder Iris / FM / FM-02-036-B | 3 | Pcs | TBRM /MO/00923 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4716_4c4a0d26 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0028] Optics Mount / FM / FM-02-038-B | 6 | Pcs | TBRM /MO/00924 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4717_909fa156 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0029] Mirror Holder / FM / FM-02-033-B | 6 | Pcs | TBRM /MO/00925 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4718_523d3f73 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0030] Lens Fix / FM / FM-02-009-B | 6 | Pcs | TBRM /MO/00926 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4719_723f6c05 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0031] Lens Mechanism 2 / FM / FM-02-004-B | 3 | Pcs | TBRM /MO/00927 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4720_659c05f3 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0032] Lens Support / FM / FM-02-042-B | 3 | Pcs | TBRM /MO/00928 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4721_0539c99d | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0033] Detector Mount / FM / FM-02-044-B | 3 | Pcs | TBRM /MO/00929 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4722_444501b5 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0034] Base / FM / FM-02-018-B | 3 | Pcs | TBRM /MO/00930 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4723_555adf8b | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0035] SA Housing / FM / FM-02-017-B | 3 | Pcs | TBRM /MO/00931 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4724_1d73f816 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0036] LS Actuator Arm / FM / FM-02-029-B | 3 | Pcs | TBRM /MO/00932 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4725_e97cad43 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0037] SA Lens Mount / FM / FM-02-020-B | 3 | Pcs | TBRM /MO/00933 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4726_28598974 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0038] Swing / FM / FM-02-019-B | 3 | Pcs | TBRM /MO/00934 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4727_c2b6bd32 | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0039] Lens Shim / FM / FM-02-061-B | 6 | Pcs | TBRM /MO/00935 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-08-25 10:59 | __export__.mrp_production_4728_f118fdfa | FALSE | 2025-08-25 10:59 | Normal | [7001-2580-0040] Window Holder / FM / FM-02-041-B | 18 | Pcs | TBRM /MO/00936 | S03443 | 2025-10-06 01:00 | 2025-10-06 02:00 | Draft | 2025-10-06 02:00
TBRM Machining B.V. |  | 2025-09-04 12:44 | __export__.mrp_production_4863_14ff79c8 | FALSE | 2025-09-04 12:44 | Normal | [00528-02424-A] Y force limit body / FME | 1 | Pcs | TBRM /MO/00974 | S03478 | 2025-10-08 01:00 | 2025-10-08 02:00 | Draft | 2025-10-08 02:00
TBRM Machining B.V. |  | 2025-09-04 12:44 | __export__.mrp_production_4864_53ebef9a | FALSE | 2025-09-04 12:44 | Normal | [00528-02426-A] Z floating body / FME | 1 | Pcs | TBRM /MO/00975 | S03478 | 2025-10-08 01:00 | 2025-10-08 02:00 | Draft | 2025-10-08 02:00
TBRM Machining B.V. |  | 2025-09-04 12:44 | __export__.mrp_production_4865_bdc6c519 | FALSE | 2025-09-04 12:44 | Normal | [00528-02428-B] Rear shaft support / FME | 1 | Pcs | TBRM /MO/00976 | S03478 | 2025-10-08 01:00 | 2025-10-08 02:00 | Draft | 2025-10-08 02:00
TBRM Machining B.V. |  | 2025-09-04 12:44 | __export__.mrp_production_4866_5df1cd14 | FALSE | 2025-09-04 12:44 | Normal | [00528-02765-A] X flexure Rx alignment tool back plate / FME | 1 | Pcs | TBRM /MO/00977 | S03478 | 2025-10-08 01:00 | 2025-10-08 02:00 | Draft | 2025-10-08 02:00
TBRM Machining B.V. |  | 2025-09-04 12:44 | __export__.mrp_production_4867_7e8a8e8a | FALSE | 2025-09-04 12:44 | Normal | [00528-02794-B] Front air bearing support block / FME | 1 | Pcs | TBRM /MO/00978 | S03478 | 2025-10-08 01:00 | 2025-10-08 02:00 | Draft | 2025-10-08 02:00
TBRM Machining B.V. |  | 2025-09-04 12:44 | __export__.mrp_production_4868_1a4b9c0b | FALSE | 2025-09-04 12:44 | Normal | [00528-02795-B] Front Z moving body / FME | 1 | Pcs | TBRM /MO/00979 | S03478 | 2025-10-08 01:00 | 2025-10-08 02:00 | Draft | 2025-10-08 02:00
TBRM Machining B.V. |  | 2025-09-05 14:27 | __export__.mrp_production_4871_5e082f5b | FALSE | 2025-09-05 14:27 | Normal | [7005-2580-0014] Backplate V01-00 / NFI / 27244701 | 6 | Pcs | TBRM /MO/00982 | S03484 | 2025-10-10 01:00 | 2025-10-10 02:00 | Draft | 2025-10-10 02:00
TBRM Machining B.V. |  | 2025-09-05 14:27 | __export__.mrp_production_4872_7bb49bea | FALSE | 2025-09-05 14:27 | Normal | [7005-2580-0015] Baseplate V01-00 / NFI / 27244702 | 1 | Pcs | TBRM /MO/00983 | S03484 | 2025-10-10 01:00 | 2025-10-10 02:00 | Draft | 2025-10-10 02:00
TBRM Machining B.V. | Available | 2025-09-03 17:30 | __export__.mrp_production_4848_336bef31 | FALSE | 2025-09-11 14:14 | Normal | LD Switch Plate / VDM / P00704 | 4 | Pcs | TBRM /MO/00959 | S03476 | 2025-10-10 02:00 | 2025-10-31 01:00 | Confirmed | 2025-10-31 01:00 | [5601-0000-0056] ALU 7075 T651 (wgw) gzgd plaat 150x30 | __export__.product_product_14412_72e466c9 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 19 | FALSE
[19 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | 108 | FALSE
TBRM Machining B.V. | Not Available | 2025-09-03 17:30 | __export__.mrp_production_4849_870681e2 | FALSE | 2025-09-11 17:05 | Normal | LD 16x Inlet Plate / VDM / P00706 | 4 | Pcs | TBRM /MO/00960 | S03476 | 2025-10-10 02:00 | 2025-10-31 01:00 | Confirmed | 2025-10-31 01:00 | [5602-0000-0005] RVS 304/304L wgw plat 70x30 | __export__.product_product_14172_f3527b5e | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 19 | FALSE
[19 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | 348 | FALSE
TBRM Machining B.V. |  | 2025-09-10 15:47 | __export__.mrp_production_4880_46e1c05c | FALSE | 2025-09-10 15:47 | Normal | [VH-C-10-100-220] Meeneemblok | 5 | Pcs | TBRM /MO/00990 | S03500 | 2025-10-13 01:00 | 2025-10-13 02:00 | Draft | 2025-10-13 02:00
TBRM Machining B.V. |  | 2025-09-10 15:47 | __export__.mrp_production_4881_d8ba1b9a | FALSE | 2025-09-10 15:47 | Normal | [VH-C-10-100-221] Steun printerbok boven | 5 | Pcs | TBRM /MO/00991 | S03500 | 2025-10-13 01:00 | 2025-10-13 02:00 | Draft | 2025-10-13 02:00
TBRM Machining B.V. |  | 2025-09-10 15:47 | __export__.mrp_production_4882_00b8fbea | FALSE | 2025-09-10 15:47 | Normal | [VH-C-10-100-222] Afdekplaat | 5 | Pcs | TBRM /MO/00992 | S03500 | 2025-10-13 01:00 | 2025-10-13 02:00 | Draft | 2025-10-13 02:00
TBRM Machining B.V. | Available | 2025-08-07 10:59 | __export__.mrp_production_4592_47cd4d22 | TRUE | 2025-08-21 09:10 | Normal | [4512-127-05186B] Anschlag | 1944 | Pcs | TBRM /MO/00877 | OP/14097 - S03398 | 2025-10-20 02:00 | 2025-11-12 14:15 | Confirmed | 2025-08-28 13:00 | [5990-0000-0012] Ensat-SBS zelfsn.draadbus M6x12 Stl.gh. | __export__.product_product_15107_d0c7b2b3 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | 1959 | FALSE
[16 empty] | [5601-0000-0008] ALU 6082 T6 plat 40x20 | __export__.product_product_14150_a5d5cc8b | 0
[19 empty] | M4-01 - Accuwell - 4axis - Conveyor automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | 3978 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 1944 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 1944 | FALSE
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4842_3771e7d0 | FALSE | 2025-09-03 17:30 | Normal | LD plate support left bottom / VDM / P03020 | 4 | Pcs | TBRM /MO/00953 | S03476 | 2025-10-31 | 2025-10-31 01:00 | Draft | 2025-10-31 01:00
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4843_0b8f9dcc | FALSE | 2025-09-03 17:30 | Normal | LD plate support left top / VDM / P03021 | 4 | Pcs | TBRM /MO/00954 | S03476 | 2025-10-31 | 2025-10-31 01:00 | Draft | 2025-10-31 01:00
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4844_b09969ad | FALSE | 2025-09-03 17:30 | Normal | LD plate support right bottom / VDM / P03022 | 4 | Pcs | TBRM /MO/00955 | S03476 | 2025-10-31 | 2025-10-31 01:00 | Draft | 2025-10-31 01:00
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4845_7f70820c | FALSE | 2025-09-03 17:30 | Normal | LD plate support right top / VDM / P03023 | 4 | Pcs | TBRM /MO/00956 | S03476 | 2025-10-31 | 2025-10-31 01:00 | Draft | 2025-10-31 01:00
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4846_138e2f61 | FALSE | 2025-09-03 17:30 | Normal | LD Mouting Plate / VDM / P00700 | 4 | Pcs | TBRM /MO/00957 | S03476 | 2025-10-31 | 2025-10-31 01:00 | Draft | 2025-10-31 01:00
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4847_50bcb0aa | FALSE | 2025-09-03 17:30 | Normal | Plate Support Upper / VDM / P00703 | 4 | Pcs | TBRM /MO/00958 | S03476 | 2025-10-31 | 2025-10-31 01:00 | Draft | 2025-10-31 01:00
TBRM Machining B.V. |  | 2025-09-03 17:30 | __export__.mrp_production_4850_1ce46f76 | FALSE | 2025-09-03 17:30 | Normal | LD coverplate / VDM / P00707 | 4 | Pcs | TBRM /MO/00961 | S03476 | 2025-10-31 | 2025-10-31 01:00 | Draft | 2025-10-31 01:00
TBRM Machining B.V. |  | 2025-09-10 17:51 | __export__.mrp_production_4888_ce0bcf78 | FALSE | 2025-09-10 17:53 | Normal | [4022.706.24672] EXE IL IXF MOD TA ADPT P BATT / HQP | 8 | Pcs | TBRM /MO/00995 | S03502 | 2025-11-03 | 2025-11-03 01:00 | Draft | 2025-11-03 01:00
TBRM Machining B.V. |  | 2025-09-10 17:51 | __export__.mrp_production_4889_2a33f300 | FALSE | 2025-09-10 17:53 | Normal | [4022.706.24682] EXE IL IXF TA ADPT P BATT MID / HQP | 4 | Pcs | TBRM /MO/00996 | S03502 | 2025-11-03 | 2025-11-03 01:00 | Draft | 2025-11-03 01:00
TBRM Machining B.V. |  | 2025-09-10 17:51 | __export__.mrp_production_4890_fefe7d7b | FALSE | 2025-09-10 17:53 | Normal | [4022.706.05882] EXE IL IXF MOD TA GUIDE / HQP | 16 | Pcs | TBRM /MO/00997 | S03502 | 2025-11-03 | 2025-11-03 01:00 | Draft | 2025-11-03 01:00
TBRM Machining B.V. | Available | 2025-08-19 10:08 | __export__.mrp_production_4686_6722c6ae | TRUE | 2025-09-03 13:14 | Normal | [BD50-5085-013-C] bracket | 40 | Pcs | TBRM /MO/00898 | S03433 | 2025-12-18 01:00 | 2026-01-08 08:29 | In Progress | 2026-01-08 01:00 | [5601-0000-0021] ALU 7075 T79511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 40 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 330 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 80 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 40 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 40 | FALSE
TBRM Machining B.V. | Available | 2025-08-19 09:36 | __export__.mrp_production_4682_124f4246 | TRUE | 2025-09-03 13:12 | Normal | [BD50-5075-011-E] bracket | 40 | Pcs | TBRM /MO/00894 | S03424 | 2026-01-09 01:00 | 2026-02-11 14:29 | In Progress | 2026-02-13 01:00 | [5601-0000-0021] ALU 7075 T79511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | 40 | FALSE
[19 empty] | M3-01 - Accuwell - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | 250 | FALSE
[19 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | 80 | FALSE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 40 | FALSE
[19 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | 4500 | TRUE
[19 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | 40 | FALSE