## Sheet1
Company | Component Status | Created on | ID | Its Operations are Planned | Last Updated on | Priority | Product | Product/ID | Quantity To Produce | Unit | Reference | Source | Start | End | State | Deadline | Components/Product | Components/Product/ID | Components/Quantity To Consume | Work Orders/Work Center | Work Orders/Work Center/ID | Work Orders/Operation | Work Orders/Bill of Material/Subcontract | Work Orders/Manufacturing Order/Expected Duration | Work Orders/Expected Duration | Work Orders/Start | Work Orders/End | Work Orders/Status
TBRM Machining B.V. | Available | 2024-12-18 12:47 | __export__.mrp_production_1104_d3ae4426 | TRUE | 2026-08-19 10:28 | Normal | [4022-651-55002A] Gpas preamp CB Box + cover assy | 14975 | 27 | Pcs | TBRM /MO/00333 |  | 2025-02-28 11:31 | 2025-03-10 10:13 | To Close |  | [5602-0000-0023] RVS 316L wgw vk 80 | __export__.product_product_14190_b2f6cfa7 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 42 | 42 | 2025-02-28 11:31 | 2026-03-23 08:52 | Finished
TBRM Machining B.V. | Available | 2026-03-17 13:47 | __export__.mrp_production_6020_2cead996 | TRUE | 2026-03-23 10:51 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 15022 | 80 | Pcs | TBRM /MO/01175-002 | S03762 | 2026-01-29 01:00 | 2026-03-19 01:00 | In Progress | 2026-03-19 10:00 | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 2715.79 | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling (FR3_01) | FALSE | 11915 | 410 | 2026-03-23 10:51 | 2026-03-23 10:51 | Finished
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 11915 | 240 | 2026-08-19 10:29 | 2026-08-19 14:59 | In Progress
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Painting | FALSE | 11915 | 9000 | 2026-09-01 10:58 | 2026-09-29 08:58 | In Progress
[20 empty] | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 11915 | 95 |  |  | Cancelled
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 11915 | 2090 |  |  | Cancelled
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 11915 | 80 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-01-15 09:58 | __export__.mrp_production_5495_6bea93ed | FALSE | 2026-08-19 10:31 | Normal | [1207568A] Cable clamp | 14912 | 30 | Pcs | TBRM /MO/01300 | S03941 | 2026-02-09 01:00 | 2026-03-16 01:00 | Confirmed | 2026-12-31 09:00 | [5606-0000-0002] PTFE Staf FG-10/2011 XT Wit Ø10 | __export__.product_product_16574_8d0c6593 | 0 | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling - OP1 | FALSE | 690 | 660 |  |  | To Do
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 690 | 30 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-04-16 15:13 | __export__.mrp_production_6199_a3feca82 | TRUE | 2026-06-16 09:44 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 15022 | 92 | Pcs | TBRM /MO/01414-002 | S04060 | 2026-04-16 15:13 | 2026-06-04 15:13 | In Progress | 2026-04-10 02:00 | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 24369.27 | 107 |  |  | Cancelled
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 24369.27 | 2390 |  |  | Cancelled
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 24369.27 | 458 |  |  | Cancelled
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 24369.27 | 276 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Painting | FALSE | 24369.27 | 21046.27 | 2026-06-16 09:44 | 2026-08-19 10:30 | Finished
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 24369.27 | 92 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-03-31 11:08 | __export__.mrp_production_6126_02e4cab5 | TRUE | 2026-08-19 10:31 | Normal | [4022-333-11506] lagerblok | 14916 | 86 | Pcs | TBRM /MO/01615 | OP/14116 - S04273 | 2026-04-17 13:00 | 2026-05-08 13:00 | In Progress | 2026-12-31 12:00 | [5602-0000-0041] RVS 430F blank rond 50h9 | __export__.product_product_15120_10aecd71 | 1725 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 2951 | 101 | 2026-04-17 13:00 | 2026-04-17 13:00 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 2951 | 176 |  |  | To Do
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR5_01) | FALSE | 2951 | 1896 |  |  | Blocked
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 2951 | 520 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 2951 | 172 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 2951 | 86 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-03 09:39 | __export__.mrp_production_7105_95a83878 | TRUE | 2026-08-19 10:32 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 15022 | 89 | Pcs | TBRM /MO/01624-002 | S04282 | 2026-05-08 02:00 | 2026-06-26 02:00 | In Progress | 2026-06-26 02:00 | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 12221 | 104 |  |  | Cancelled
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 12221 | 2315 | 2026-08-19 10:32 | 2026-08-19 10:32 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 12221 | 446 | 2026-08-19 10:32 | 2026-08-19 10:32 | Finished
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 12221 | 267 | 2026-08-19 10:32 | 2026-08-19 15:29 | In Progress
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Painting | FALSE | 12221 | 9000 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 12221 | 89 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-05-11 10:42 | __export__.mrp_production_6300_645dbbde | FALSE | 2026-05-11 10:42 | Normal | [4022-637-29301] Hinge Block Fixed RM | 14964 | 17 | Pcs | TBRM /MO/01266-002 | S03870 | 2026-05-11 10:42 | 2026-06-01 10:42 | Confirmed | 2026-01-16 10:00 | [5602-0000-0003] RVS 304/304L wgw plat 40x30 | __export__.product_product_14170_ab4f36b5 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 880 | 32 |  |  | Cancelled
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 880 | 430 |  |  | Cancelled
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 880 | 175 |  |  | Cancelled
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 880 | 175 |  |  | Cancelled
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 880 | 51 |  |  | To Do
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 880 | 17 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-06 16:55 | __export__.mrp_production_7200_dd78e2c4 | FALSE | 2026-07-06 16:58 | Normal | [4022.620.02663] RH NXE RED FIDUCIAL MOUNT BRKT | 18665 | 1 | Pcs | TBRM /MO/01750-002 | S04500 | 2026-06-03 02:00 | 2026-06-24 02:00 | Confirmed | 2026-06-24 02:00 | [5601-0000-0185] ALU 5083 gegoten 6z gezaagd 200x15 | __export__.product_product_17610_12e3ccef | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 7136 | 16 |  |  | Cancelled
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | PRE | FALSE | 7136 | 108 |  |  | Cancelled
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP1 | FALSE | 7136 | 131 |  |  | Cancelled
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 7136 | 131 |  |  | Cancelled
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Nickel Plating | FALSE | 7136 | 2250 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Clean PG1 / MG2 | FALSE | 7136 | 4500 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-05-26 08:41 | __export__.mrp_production_6426_14647c79 | TRUE | 2026-07-08 14:18 | Normal | [GF3116T006L] Carriage | 15035 | 240 | Pcs | TBRM /MO/01743 | OP/14094 - S04481 | 2026-06-05 02:00 | 2026-07-15 16:24 | In Progress | 2026-07-10 02:00 | [5601-0000-0001] ALU 5083 6z gzgd plaat 120x110x15 | __export__.product_product_14143_fa3ca59e | 240 | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling OP1 | FALSE | 15090 | 330 | 2026-06-10 16:24 | 2026-07-28 15:08 | Finished
[17 empty] | [5302-0000-0003] Airbubbled bag with closure strip 150x200mm / Van Gennip / 550423 | __export__.product_product_17642_0164f9b0 | 240
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling OP2 | FALSE | 15090 | 6570 | 2026-07-28 15:08 | 2026-07-28 15:08 | Finished
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling OP3 | FALSE | 15090 | 3450 | 2026-08-19 10:33 | 2026-08-25 15:33 | In Progress
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Nickel plating | FALSE | 15090 | 4500 | 2026-07-28 15:09 | 2026-08-11 14:08 | In Progress
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 15090 | 240 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-04-23 12:35 | __export__.mrp_production_6209_9f61b525 | TRUE | 2026-09-08 09:23 | Normal | [00429-00-662-B] Arret lever | 14895 | 420 | Pcs | TBRM /MO/01672 | OP/14108 | 2026-06-10 15:53 | 2026-07-01 15:53 | In Progress | 2026-05-14 12:00 | [5601-0000-0014] ALU 6082 T6 vk 35 | __export__.product_product_14156_fd7d53c1 | 120000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 465 | 35 | 2026-06-10 15:53 | 2026-06-10 15:53 | Finished
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 465 | 370 | 2026-08-19 10:33 | 2026-08-19 10:33 | Finished
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | Milling (FR3-01) | FALSE | 465 | 40 |  |  | To Do
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 465 | 20 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-04-23 12:35 | __export__.mrp_production_6210_afc3a4ad | TRUE | 2026-07-27 14:53 | Normal | [1508130 B] [Q] excenter housing z | 16893 | 134 | Pcs | TBRM /MO/01673 | OP/14150 | 2026-06-10 15:54 | 2026-07-31 08:27 | In Progress | 2026-05-14 12:00 | [5601-0000-0012] ALU 6082 T6 plat 60x40 | __export__.product_product_14154_75692b32 | 12000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 9029 | 175 | 2026-06-10 15:54 | 2026-06-10 15:54 | Finished
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR5_01) | FALSE | 9029 | 7290 | 2026-06-10 15:54 | 2026-08-19 10:35 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 9029 | 760 | 2026-08-19 10:35 | 2026-08-19 10:35 | Finished
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 9029 | 670 | 2026-07-29 11:03 | 2026-07-30 14:43 | To Do
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 9029 | 134 | 2026-07-30 14:43 | 2026-07-31 08:27 | Blocked
TBRM Machining B.V. | Available | 2026-06-02 09:01 | __export__.mrp_production_6438_7d858fb4 | TRUE | 2026-08-27 09:42 | Normal | [4022.704.19332] RH RED STATIC STRAIN RELIEF B | 7365 | 71 | Pcs | TBRM /MO/01751 | S04501 | 2026-06-15 02:00 | 2026-09-08 09:25 | In Progress | 2026-07-20 02:00 | [5602-0000-0025] RVS 316L wgw plat 40x15 | __export__.product_product_14192_26c9adbe | 1760 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 6646 | 95 | 2026-08-19 10:36 | 2026-08-19 10:36 | Finished
[20 empty] | UMC750SS-2 | __export__.mrp_workcenter_62_468a38e5 | Machining (M5-04) | FALSE | 6646 | 1980 | 2026-08-19 10:37 | 2026-08-19 10:37 | Finished
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivate + Engraving + Cleaning | FALSE | 6646 | 4500 | 2026-08-26 19:05 | 2026-09-08 08:14 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 6646 | 71 | 2026-09-08 08:14 | 2026-09-08 09:25 | Blocked
TBRM Machining B.V. | Available | 2026-06-19 12:57 | __export__.mrp_production_7003_03b81406 | FALSE | 2026-07-03 10:19 | Normal | [7007-2500-0010] 263 - EL5 Bottom Side Panel Right (Dark) No Coating / IAH / 2026.SPX.0263.20.20 | 19199 | 1 | Pcs | TBRM /MO/01797 | Manual Replenishment | 2026-06-19 12:57 | 2026-07-10 12:57 | Confirmed | 2026-07-10 12:57 | [5601-0000-0228] ALU 5083 gegoten gefreesd 965x423x40mm | __export__.product_product_19248_d135bc79 | 0 | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP1 | FALSE | 300 | 150 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 300 | 150 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-08 14:21 | __export__.mrp_production_7904_d06a42f4 | FALSE | 2026-09-08 14:24 | Normal | [4022.645.57761] RH NXE RBI COVER HOUSING | 19387 | 20 | Pcs | TBRM /MO/01734-003 | S04460 | 2026-07-08 02:00 | 2026-07-29 02:00 | Confirmed | 2026-07-29 02:00 | [5601-0000-0233] ALU 6082 T651 (wgw) gzgd plaat 360x275x140 | __export__.product_product_19575_f523d659 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  | FALSE | 9435 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  | FALSE | 9435 | 90 |  |  | Blocked
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP1 | FALSE | 9435 | 1290 |  |  | Blocked
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 9435 | 1290 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | TiN | FALSE | 9435 | 6750 |  |  | To Do
TBRM Machining B.V. | Available | 2026-05-19 13:28 | __export__.mrp_production_6391_80325cfc | TRUE | 2026-08-19 10:48 | Normal | [4022-666-3837-1] LSPH Bellow Clamp | 14985 | 200 | Pcs | TBRM /MO/01735 | S04466 | 2026-07-16 02:00 | 2026-09-16 10:48 | In Progress | 2026-08-13 02:00 | [5990-0000-0017] LSPH Bellow Clamp cutout | __export__.product_product_15112_c44437c2 | 200 | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 2380 | 1090 | 2026-08-19 10:48 | 2026-08-19 10:48 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 2380 | 690 | 2026-08-19 10:48 | 2026-08-19 10:48 | Finished
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 2380 | 400 | 2026-08-19 10:48 | 2026-08-20 09:28 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 2380 | 200 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-06 14:05 | __export__.mrp_production_7132_e96ed3ac | TRUE | 2026-08-19 10:49 | Normal | [7001-2580-0045] ST Spring Housing / FM / FM2010-M00011 Rev. D | 18722 | 20 | Pcs | TBRM /MO/01868 | S04658 | 2026-07-20 02:00 | 2026-09-09 10:49 | In Progress | 2026-08-10 02:00 | [5605-0000-0044] POM TECAFORM AH LM white plate 230x75x20 | __export__.product_product_17888_ac4e8020 | 4 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 628 | 4 | 2026-08-19 10:49 | 2026-08-19 10:49 | Finished
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | OP1 | FALSE | 628 | 316 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | OP2 | FALSE | 628 | 248 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Engrave | FALSE | 628 | 60 |  |  | Blocked
TBRM Machining B.V. | Exp 09/09/2026 | 2026-08-27 15:29 | __export__.mrp_production_7886_c28135b6 | FALSE | 2026-08-27 15:29 | Normal | [7001-2580-0007] ST Interface plate / FM / FM210-M00008 Rev. D | 17701 | 20 | Pcs | TBRM /MO/01872-002 | S04658 | 2026-07-20 02:00 | 2026-08-10 02:00 | Confirmed | 2026-08-10 02:00 | [5605-0000-0044] POM TECAFORM AH LM white plate 230x75x20 | __export__.product_product_17888_ac4e8020 | 0 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 590 | 4 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 590 | 136 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Engrave | FALSE | 590 | 450 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-16 15:03 | __export__.mrp_production_7596_c18ab2f0 | TRUE | 2026-08-19 10:54 | Normal | [4022.695.89661] MBI WS MK2 AORTA BRACE IF | 19106 | 26 | Pcs | TBRM /MO/02303 | S04766 | 2026-07-29 02:00 | 2026-09-09 10:54 | In Progress | 2026-08-19 02:00 | [5602-0000-0016] RVS 304/304L wgw plat 100x30 | __export__.product_product_14183_29d28557 | 1500 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 3341 | 41 | 2026-08-19 10:54 | 2026-08-19 10:54 | Finished
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP1 | FALSE | 3341 | 1650 |  |  | To Do
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP2 | FALSE | 3341 | 1650 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-01 12:36 | __export__.mrp_production_7892_d930c103 | TRUE | 2026-09-10 09:29 | Normal | [4022.704.19282] RH RED GRIPPER BODY | 14210 | 34 | Pcs | TBRM /MO/01644-003 | S04308 | 2026-08-04 02:00 | 2026-11-03 16:06 | In Progress | 2026-08-25 02:00 | [5602-0000-0060] RVS 316/316L 1 richting gzgd plaat 210x105x30 (tol. -0/+3mm) | __export__.product_product_17381_95528666 | 34 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 22864 | 34 |  |  | Cancelled
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Milling - OP1/2 | FALSE | 22864 | 2100 |  |  | Cancelled
[20 empty] | UMC750-3 | __export__.mrp_workcenter_83_95c50e96 | Milling - OP3/4 | FALSE | 22864 | 16380 | 2026-09-01 12:36 | 2026-10-21 11:06 | In Progress
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Milling - OP5 | FALSE | 22864 | 2100 | 2026-10-21 11:06 | 2026-10-28 08:06 | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivation, Bake-out, Cleaning and Packing according to drawing | FALSE | 22864 | 2250 | 2026-10-28 08:06 | 2026-11-03 16:06 | Blocked
TBRM Machining B.V. | Available | 2026-07-07 14:54 | __export__.mrp_production_7203_0e606185 | TRUE | 2026-09-03 11:04 | Normal | [4023-001-43251B] Block detection RI | 15010 | 15 | Pcs | TBRM /MO/01938 | OP/14082 - S04670 | 2026-08-07 02:00 | 2026-09-30 10:56 | In Progress | 2026-09-18 02:00 | [5601-0000-0007] ALU 6082 T6 vk 30 | __export__.product_product_14149_55705e3a | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 2685 | 30 | 2026-08-19 10:56 | 2026-08-19 10:56 | Finished
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR5_01) | FALSE | 2685 | 180 | 2026-09-10 15:05 | 2026-09-10 15:05 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 2685 | 210 | 2026-09-10 15:05 | 2026-09-10 15:05 | Finished
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodising | FALSE | 2685 | 2250 | 2026-09-10 15:06 | 2026-09-17 14:36 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 2685 | 15 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7228_7fa52c80 | TRUE | 2026-09-10 12:27 | Normal | [7001-2580-0023] TOP PLATE / FM / FM-02-003-C | 17773 | 10 | Pcs | TBRM /MO/01943 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:57 | In Progress | 2026-09-02 02:00 | [5601-0000-0196] ALU 6082 T651 (wgw) gzgd plaat 675x325x15 | __export__.product_product_18108_743e1bbb | 10 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 4460 | 10 | 2026-08-19 10:57 | 2026-08-19 10:57 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP1 | FALSE | 4460 | 740 | 2026-09-10 12:27 | 2026-09-14 10:20 | In Progress
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 4460 | 1460 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 4460 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7229_67d38ddc | TRUE | 2026-09-10 12:37 | Normal | [7001-2580-0024] LIGHT L BRACKET / FM / FM-02-030-B | 17774 | 10 | Pcs | TBRM /MO/01944 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:57 | In Progress | 2026-09-02 02:00 | [5601-0000-0194] ALU 6082 T651 (wgw) gzgd plaat 300x225x70 | __export__.product_product_18095_f7459746 | 10 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 3790 | 10 | 2026-08-19 10:57 | 2026-08-19 10:57 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 3790 | 1530 | 2026-09-10 12:37 | 2026-09-15 16:07 | In Progress
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 3790 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7242_b4af134d | TRUE | 2026-08-19 10:57 | Normal | [7001-2580-0029] Mirror Holder / FM / FM-02-033-B | 17779 | 20 | Pcs | TBRM /MO/01957 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:57 | In Progress | 2026-09-02 02:00 | [5601-0000-0030] ALU 6082 T651 (wgw) gzgd plaat 75x50 | __export__.product_product_14386_609519d6 | 1900 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 3265 | 35 | 2026-08-19 10:57 | 2026-08-19 10:57 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 3265 | 980 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 3265 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7243_e2cb2571 | TRUE | 2026-08-19 10:57 | Normal | [7001-2580-0030] Lens Fix / FM / FM-02-009-B | 17780 | 20 | Pcs | TBRM /MO/01958 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:57 | In Progress | 2026-09-02 02:00 | [5601-0000-0022] ALU 6082 T651 (wgw) gzgd plaat 50x30 | __export__.product_product_14378_27610464 | 1600 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2885 | 35 | 2026-08-19 10:57 | 2026-08-19 10:57 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2885 | 600 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2885 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7244_212122d6 | TRUE | 2026-08-19 10:57 | Normal | [7001-2580-0031] Lens Mechanism 2 / FM / FM-02-004-B | 17781 | 10 | Pcs | TBRM /MO/01959 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:57 | In Progress | 2026-09-02 02:00 | [5601-0000-0198] ALU 6082 T651 (wgw) gzgd plaat 160x120x90 | __export__.product_product_18118_5f42d2af | 10 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 3170 | 10 | 2026-08-19 10:57 | 2026-08-19 10:57 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 3170 | 910 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 3170 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7255_0b10a354 | TRUE | 2026-08-19 10:58 | Normal | [7001-2580-0034] Base / FM / FM-02-018-B | 17784 | 10 | Pcs | TBRM /MO/01970 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:58 | In Progress | 2026-09-02 02:00 | [5601-0000-0024] ALU 6082 T651 (wgw) gzgd plaat 100x30 | __export__.product_product_14380_4f95a69e | 800 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2615 | 25 | 2026-08-19 10:58 | 2026-08-19 10:58 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling OP1/OP2 | FALSE | 2615 | 340 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2615 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7256_ef4919a9 | TRUE | 2026-08-19 10:58 | Normal | [7001-2580-0035] SA Housing / FM / FM-02-017-B | 17785 | 10 | Pcs | TBRM /MO/01971 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:58 | In Progress | 2026-09-02 02:00 | [5601-0000-0030] ALU 6082 T651 (wgw) gzgd plaat 75x50 | __export__.product_product_14386_609519d6 | 1100 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2865 | 25 | 2026-08-19 10:58 | 2026-08-19 10:58 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling OP1/OP2 | FALSE | 2865 | 590 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2865 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7257_de9f34e4 | TRUE | 2026-08-19 10:58 | Normal | [7001-2580-0036] LS Actuator Arm / FM / FM-02-029-B | 17786 | 10 | Pcs | TBRM /MO/01972 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:58 | In Progress | 2026-09-02 02:00 | [5601-0000-0023] ALU 6082 T651 (wgw) gzgd plaat 75x30 | __export__.product_product_14379_b8846587 | 300 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2595 | 25 | 2026-08-19 10:58 | 2026-08-19 10:58 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2595 | 320 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2595 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7261_d0b8d6cf | TRUE | 2026-08-19 10:58 | Normal | [7001-2580-0038] Swing / FM / FM-02-019-B | 17788 | 10 | Pcs | TBRM /MO/01976 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:58 | In Progress | 2026-09-02 02:00 | [5601-0000-0022] ALU 6082 T651 (wgw) gzgd plaat 50x30 | __export__.product_product_14378_27610464 | 750 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2615 | 25 | 2026-08-19 10:58 | 2026-08-19 10:58 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2615 | 340 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2615 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7282_5b54ffc7 | TRUE | 2026-08-19 10:58 | Normal | [7001-2580-0018] Mountblock / FM / FM-02-013-B | 17768 | 60 | Pcs | TBRM /MO/01997 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:58 | In Progress | 2026-09-02 02:00 | [5601-0000-0022] ALU 6082 T651 (wgw) gzgd plaat 50x30 | __export__.product_product_14378_27610464 | 1800 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 6825 | 3615 | 2026-08-19 10:58 | 2026-08-19 10:58 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 6825 | 960 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 6825 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 00:56 | __export__.mrp_production_7293_d55f3b9e | TRUE | 2026-08-19 10:59 | Normal | [7001-2540-0009] Mirror Holder V2 / FM-02-034 | 17904 | 10 | Pcs | TBRM /MO/02008 | S04685 | 2026-08-12 02:00 | 2026-09-09 10:59 | In Progress | 2026-09-02 02:00 | [5601-0000-0030] ALU 6082 T651 (wgw) gzgd plaat 75x50 | __export__.product_product_14386_609519d6 | 900 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2755 | 25 | 2026-08-19 10:59 | 2026-08-19 10:59 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2755 | 480 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodise (black) | FALSE | 2755 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:15 | __export__.mrp_production_7503_32aed582 | TRUE | 2026-09-08 14:32 | Normal | [7001-2580-0022] HOLDER CREDIT CARD / FM / FM-02-007-C | 17772 | 9 | Pcs | TBRM /MO/02218 | TBRM /MO/02005,TBRM /MO/02006,TBRM /MO/02007 | 2026-08-12 02:00 | 2026-09-09 10:44 | In Progress | 2026-09-02 02:00 | [5601-0000-0035] ALU 6082 T651 (wgw) gzgd plaat 200x50 | __export__.product_product_14391_7229d07d | 1500 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 3213 | 18 | 2026-08-19 10:44 | 2026-08-19 10:44 | Finished
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling OP1 | FALSE | 3213 | 324 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling OP2 | FALSE | 3213 | 621 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 3213 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:16 | __export__.mrp_production_7504_01871cc0 | TRUE | 2026-09-08 14:34 | Normal | [7001-2580-0020] Monitor Support 2 / FM / FM-02-045-B | 17770 | 18 | Pcs | TBRM /MO/02219 | TBRM /MO/02001,TBRM /MO/02002,TBRM /MO/02003 | 2026-08-12 02:00 | 2026-09-09 10:44 | In Progress | 2026-09-02 02:00 | [5601-0000-0036] ALU 6082 T651 (wgw) gzgd plaat 200x15 | __export__.product_product_14392_8b21e679 | 870 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2372 | 18 | 2026-08-19 10:44 | 2026-08-19 10:44 | Finished
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 2372 | 104 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2372 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:16 | __export__.mrp_production_7505_7d13bf71 | TRUE | 2026-09-04 16:08 | Normal | [7001-2580-0019] Monitor Support / FM / FM-02-046-B | 17769 | 18 | Pcs | TBRM /MO/02220 | TBRM /MO/01998,TBRM /MO/01999,TBRM /MO/02000 | 2026-08-12 02:00 | 2026-09-09 10:44 | In Progress | 2026-09-02 02:00 | [5601-0000-0036] ALU 6082 T651 (wgw) gzgd plaat 200x15 | __export__.product_product_14392_8b21e679 | 870 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2379 | 18 | 2026-08-19 10:44 | 2026-08-19 10:44 | Finished
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 2379 | 111 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2379 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:16 | __export__.mrp_production_7506_7d1ab712 | TRUE | 2026-09-08 14:31 | Normal | [7001-2580-0017] Pusher / FM / FM-02-011-B | 17767 | 12 | Pcs | TBRM /MO/02221 | TBRM /MO/01995,TBRM /MO/01996 | 2026-08-12 02:00 | 2026-09-09 10:44 | In Progress | 2026-09-02 02:00 | [5605-0000-0016] POM-C zwart gzgd plaat 150x50 | __export__.product_product_14470_eacf2e83 | 930 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 111 | 17 | 2026-08-19 10:44 | 2026-08-19 10:44 | Finished
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 111 | 94 |  |  | To Do
TBRM Machining B.V. | Available | 2026-07-08 16:36 | __export__.mrp_production_7509_b9b854dc | TRUE | 2026-09-08 14:33 | Normal | [7001-2580-0037] SA Lens Mount / FM / FM-02-020-B | 17787 | 9 | Pcs | TBRM /MO/02224 | TBRM /MO/01973,TBRM /MO/01974,TBRM /MO/01975 | 2026-08-12 02:00 | 2026-09-09 10:45 | In Progress | 2026-09-02 02:00 | [5601-0000-0024] ALU 6082 T651 (wgw) gzgd plaat 100x30 | __export__.product_product_14380_4f95a69e | 795 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2634 | 18 | 2026-08-19 10:45 | 2026-08-19 10:45 | Finished
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 2634 | 366 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2634 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:37 | __export__.mrp_production_7511_3a4b129b | TRUE | 2026-09-04 16:08 | Normal | [7001-2580-0033] Detector Mount / FM / FM-02-044-B | 17783 | 10 | Pcs | TBRM /MO/02226 | TBRM /MO/01965,TBRM /MO/01966,TBRM /MO/01967,TBRM /MO/01968,TBRM /MO/01969 | 2026-08-12 02:00 | 2026-09-09 10:45 | In Progress | 2026-09-02 02:00 | [5601-0000-0025] ALU 6082 T651 (wgw) gzgd plaat 125x30 | __export__.product_product_14381_aabfdbd5 | 750 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2630 | 20 | 2026-08-19 10:45 | 2026-08-19 10:45 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling OP1 | FALSE | 2630 | 160 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling OP2 | FALSE | 2630 | 200 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2630 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:37 | __export__.mrp_production_7512_f750e4df | TRUE | 2026-09-08 14:35 | Normal | [7001-2580-0032] Lens Support / FM / FM-02-042-B | 17782 | 10 | Pcs | TBRM /MO/02227 | TBRM /MO/01960,TBRM /MO/01961,TBRM /MO/01962,TBRM /MO/01963,TBRM /MO/01964 | 2026-08-12 02:00 | 2026-09-09 10:45 | In Progress | 2026-09-02 02:00 | [5601-0000-0067] ALU 6082 T651 (wgw) gzgd plaat 150x60 | __export__.product_product_14423_6227eba4 | 450 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing - OP1 | FALSE | 2525 | 20 | 2026-08-19 10:45 | 2026-08-19 10:45 | Finished
[20 empty] | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Sawing - OP2 | FALSE | 2525 | 5 | 2026-08-19 10:45 | 2026-08-19 10:45 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2525 | 250 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2525 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-21 08:53 | __export__.mrp_production_7609_1ce8004f | TRUE | 2026-09-03 14:25 | Normal | [4022-680-50231] MBI WS MK2 F&T BMA CONNECT 1 | 14996 | 25 | Pcs | TBRM /MO/02306 | S04773 | 2026-08-13 02:00 | 2026-09-10 08:20 | In Progress | 2026-09-03 02:00 | [5602-0000-0050] RVS 316L wgw plat 80x40 | __export__.product_product_16581_30702b4a | 1000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 2905 | 40 | 2026-08-19 10:59 | 2026-08-19 10:59 | Finished
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling (FR3_02) | FALSE | 2905 | 615 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating+Clean | FALSE | 2905 | 2250 | 2026-09-03 08:50 | 2026-09-10 08:20 | In Progress
TBRM Machining B.V. | Available | 2026-08-25 10:34 | __export__.mrp_production_7817_03271e56 | FALSE | 2026-09-07 13:04 | Normal | [4022-659-99092] YS ML Guardrail Park Block | 14981 | 30 | Pcs | TBRM /MO/02377 | S04883 | 2026-08-13 02:00 | 2026-09-17 02:00 | Confirmed | 2026-09-17 02:00 |  |  |  | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP1 | FALSE | 2010 | 1440 |  |  | To Do
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 2010 | 30 |  |  | Blocked
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP2 | FALSE | 2010 | 540 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-25 10:34 | __export__.mrp_production_7818_f00f909e | FALSE | 2026-09-07 13:10 | Normal | [4022-659-99111] YS ML Park Block Handle | 14982 | 30 | Pcs | TBRM /MO/02378 | S04883 | 2026-08-13 02:00 | 2026-09-17 02:00 | Confirmed | 2026-09-17 02:00 |  |  |  | VF2SS | __export__.mrp_workcenter_60_6593b576 | OP1 | FALSE | 1350 | 660 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | OP2 | FALSE | 1350 | 660 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 1350 | 30 |  |  | Blocked
TBRM Machining B.V. |  | 2026-08-13 13:39 | __export__.mrp_production_7763_0bcf2bf4 | FALSE | 2026-08-13 13:39 | Normal | [4022.737.00811/AA] EXE VS YNOZ DUCT GR1 COVER | 18794 | 3 | Pcs | TBRM /MO/02372 | Manual Replenishment | 2026-08-13 12:39 | 2026-08-13 14:09 | Draft | 2026-08-13 12:39 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. | Exp 09/09/2026 | 2026-08-05 09:50 | __export__.mrp_production_7735_1f4c7274 | FALSE | 2026-09-09 13:44 | Normal | [4022.622.19821] RH NXE RBI BAFFLE INSERT | 19415 | 5 | Pcs | TBRM /MO/02359 | S04831 | 2026-08-17 02:00 | 2026-09-07 02:00 | Confirmed | 2026-09-07 02:00 | [5601-0000-0236] ALU 6082 T651 (wgw) gzgd plaat 275x 255x100 | __export__.product_product_20035_095ebd40 | 0 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 755 | 5 |  |  | To Do
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP1 | FALSE | 755 | 390 |  |  | Blocked
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | OP2 | FALSE | 755 | 360 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-04-15 12:06 | __export__.mrp_production_6192_3443eb6e | TRUE | 2026-08-18 15:57 | Normal | [M0216-01-363-B] nul-graden arretsegment | 15042 | 46 | Pcs | TBRM /MO/01368-002 | OP/14119 | 2026-08-18 09:35 | 2026-08-25 09:51 | In Progress | 2026-02-23 11:00 | [5603-0000-0018] STAAL s235jr wgw plat 70x20 | __export__.product_product_15125_1f1d8f66 | 12631.58 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 4059 | 65 |  |  | Cancelled
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling (FR3_02) | FALSE | 4059 | 228 | 2026-04-17 13:08 | 2026-04-17 13:08 | Finished
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling (FR3_02) | FALSE | 4059 | 1378 | 2026-08-19 11:00 | 2026-08-19 11:00 | Finished
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4059 | 92 | 2026-08-19 11:00 | 2026-08-19 11:00 | Finished
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 4059 | 2250 | 2026-08-18 09:35 | 2026-08-25 09:05 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4059 | 46 | 2026-08-25 09:05 | 2026-08-25 09:51 | Blocked
TBRM Machining B.V. | Available | 2026-07-28 09:47 | __export__.mrp_production_7700_a1736965 | TRUE | 2026-09-11 13:25 | Normal | [4022.683.44771] RH NXE RED RZ ENC PLATE SPPRT | 16114 | 1 | Pcs | TBRM /MO/02331 | S04812 | 2026-08-19 02:00 | 2026-10-02 13:25 | In Progress | 2026-09-09 02:00 | [5601-0000-0022] ALU 6082 T651 (wgw) gzgd plaat 50x30 | __export__.product_product_14378_27610464 | 80 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2344 | 16 | 2026-09-11 13:25 | 2026-09-11 13:25 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2344 | 78 | 2026-09-11 13:25 | 2026-09-11 13:25 | Finished
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Nickel Plating + Cleaning | FALSE | 2344 | 2250 |  |  | To Do
TBRM Machining B.V. | Available | 2026-06-25 10:42 | __export__.mrp_production_7047_47cb762c | TRUE | 2026-08-19 10:39 | Normal | [00429-00-249-A] Plint adjust strip | 14894 | 420 | Pcs | TBRM /MO/01822 | OP/14115 | 2026-08-19 10:39 | 2026-09-16 10:39 | In Progress | 2026-07-23 12:00 | [5603-0000-0013] S235JRC+C blank plat 40x10 (ca 3-3,5 mtr) | __export__.product_product_15106_3345092e | 12000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 2364 | 16 | 2026-08-19 10:39 | 2026-08-19 10:39 | Finished
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4-01) | FALSE | 2364 | 96 |  |  | To Do
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 2364 | 1 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 2364 | 2250 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 2364 | 1 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-06-25 12:20 | __export__.mrp_production_7048_35d221ef | TRUE | 2026-08-19 10:39 | Normal | [00385-00-329-A] End plate finger safety hinge | 14891 | 473 | Pcs | TBRM /MO/01823 | OP/14118 | 2026-08-19 10:39 | 2026-09-16 10:39 | In Progress | 2026-07-23 12:00 | [5603-0000-0006] STAAL S235JRC+C blank plat 20x5 | __export__.product_product_14201_02d1168d | 36000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 5193 | 488 | 2026-08-19 10:39 | 2026-08-19 10:39 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP1 | FALSE | 5193 | 1509 |  |  | To Do
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5193 | 473 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 5193 | 2250 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5193 | 473 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-06-25 12:20 | __export__.mrp_production_7049_04716836 | TRUE | 2026-08-19 10:39 | Normal | [4022-337-33842] arret holder | 14925 | 120 | Pcs | TBRM /MO/01824 | OP/14117 | 2026-08-19 10:39 | 2026-09-09 10:39 | In Progress | 2026-07-16 12:00 | [5602-0000-0041] RVS 430F blank rond 50h9 | __export__.product_product_15120_10aecd71 | 4000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 464 | 19 | 2026-08-19 10:39 | 2026-08-19 10:39 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 464 | 98 | 2026-08-19 10:39 | 2026-08-19 10:39 | Finished
[20 empty] | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 464 | 19 | 2026-08-19 10:39 | 2026-08-19 10:39 | Finished
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR5_01) | FALSE | 464 | 190 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 464 | 122 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 464 | 12 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 464 | 4 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-06-21 22:20 | __export__.mrp_production_7016_fa99c96e | TRUE | 2026-08-19 10:41 | Normal | [4022-666-18121] Distance Bush 1 | 14984 | 342 | Pcs | TBRM /MO/01809 | OP/14074 - S04572 | 2026-08-19 10:41 | 2026-09-09 10:41 | In Progress | 2026-07-21 02:00 | [5602-0000-0017] RVS 304/304L blank vk 10 | __export__.product_product_14184_848b2c42 | 6000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 4551 | 357 | 2026-08-19 10:41 | 2026-08-19 10:41 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 4551 | 3168 |  |  | To Do
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4551 | 684 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4551 | 342 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:36 | __export__.mrp_production_7508_1f261ca4 | TRUE | 2026-08-19 10:44 | Normal | [7001-2580-0040] Window Holder / FM / FM-02-041-B | 17790 | 72 | Pcs | TBRM /MO/02223 | TBRM /MO/01981,TBRM /MO/01982,TBRM /MO/01983,TBRM /MO/01984,TBRM /MO/01985,TBRM /MO/01986,TBRM /MO/01987,TBRM /MO/01988,TBRM /MO/01989,TBRM /MO/01990,TBRM /MO/01991,TBRM /MO/01992 | 2026-08-19 10:44 | 2026-09-09 10:44 | In Progress |  | [5601-0000-0024] ALU 6082 T651 (wgw) gzgd plaat 100x30 | __export__.product_product_14380_4f95a69e | 180 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2373 | 27 | 2026-08-19 10:44 | 2026-08-19 10:44 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2373 | 96 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2373 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 16:38 | __export__.mrp_production_7513_3de5056a | TRUE | 2026-08-19 10:45 | Normal | [7001-2580-0026] Holder Fresnell / FM / FM-02-035-B | 17776 | 10 | Pcs | TBRM /MO/02228 | TBRM /MO/01950,TBRM /MO/01951,TBRM /MO/01952,TBRM /MO/01953,TBRM /MO/01954 | 2026-08-19 10:45 | 2026-09-09 10:45 | In Progress |  | [5601-0000-0067] ALU 6082 T651 (wgw) gzgd plaat 150x60 | __export__.product_product_14423_6227eba4 | 475 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing OP1 | FALSE | 2670 | 20 | 2026-08-19 10:45 | 2026-08-19 10:45 | Finished
[20 empty] | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Sawing OP2 | FALSE | 2670 | 5 | 2026-08-19 10:45 | 2026-08-19 10:45 | Finished
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2670 | 395 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2670 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-16 10:40 | __export__.mrp_production_7591_7e8691ac | TRUE | 2026-08-19 10:48 | Normal | [00385-00-320-A] Plint adjust strip | 14889 | 654 | Pcs | TBRM /MO/02298 | OP/14113 | 2026-08-19 10:48 | 2026-09-16 10:48 | In Progress | 2026-08-13 12:00 | [5603-0000-0005] STAAL S235JRC+C blank plat 40x10 | __export__.product_product_14200_70254936 | 18000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 8895 | 669 | 2026-08-19 10:48 | 2026-08-19 10:48 | Finished
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4-01) | FALSE | 8895 | 4668 |  |  | To Do
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 8895 | 654 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 8895 | 2250 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 8895 | 654 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-16 10:40 | __export__.mrp_production_7592_8727887b | TRUE | 2026-09-08 09:23 | Normal | [00429-00-662-B] Arret lever | 14895 | 400 | Pcs | TBRM /MO/02299 | OP/14108 | 2026-08-19 10:48 | 2026-09-09 10:48 | In Progress | 2026-08-06 12:00 | [5601-0000-0014] ALU 6082 T6 vk 35 | __export__.product_product_14156_fd7d53c1 | 120000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 735 | 35 | 2026-08-19 10:48 | 2026-08-19 10:48 | Finished
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 735 | 490 | 2026-08-19 10:48 | 2026-08-19 10:48 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3-01) | FALSE | 735 | 190 |  |  | To Do
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 735 | 20 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-27 14:54 | __export__.mrp_production_7694_778da661 | TRUE | 2026-08-19 10:53 | Normal | [1508130 B] [Q] excenter housing z | 16893 | 174 | Pcs | TBRM /MO/02329 |  | 2026-08-19 10:53 | 2026-09-09 10:53 | In Progress |  | [5601-0000-0012] ALU 6082 T6 plat 60x40 | __export__.product_product_14154_75692b32 | 12000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 10083 | 189 | 2026-08-19 10:53 | 2026-08-19 10:53 | Finished
[20 empty] | UMC750SS-2 | __export__.mrp_workcenter_62_468a38e5 | Milling (FR5_01) | FALSE | 10083 | 7890 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 10083 | 960 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 10083 | 870 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 10083 | 174 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-16 11:06 | __export__.mrp_production_7593_91e4f0ef | TRUE | 2026-08-19 11:01 | Normal | [1011113A] Cord Bracket | 14905 | 134 | Pcs | TBRM /MO/02300 | OP/14046 - S04762 | 2026-08-19 11:01 | 2026-09-09 11:01 | In Progress | 2026-09-11 02:00 | [5604-0000-0002] MESSING CuZn40Pb2 plat 30x20 | __export__.product_product_14165_af7aab6e | 6000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 1669 | 149 | 2026-08-19 11:01 | 2026-08-19 11:01 | Finished
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4-01) | FALSE | 1669 | 760 | 2026-09-10 12:28 | 2026-09-11 11:38 | In Progress
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4-01) | FALSE | 1669 | 358 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 1669 | 268 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 1669 | 134 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-27 15:58 | __export__.mrp_production_7695_fc7ed079 | TRUE | 2026-08-19 11:01 | Normal | [4022-656-73531] Pipe clamp exhaust FW 1980 | 14976 | 86 | Pcs | TBRM /MO/02330 | OP/14069 - S04806 | 2026-08-19 11:01 | 2026-09-09 11:01 | In Progress | 2026-09-11 02:00 | [5602-0000-0013] RVS 304/304L blank plat 50x8 | __export__.product_product_14180_b574d432 | 3000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 763 | 101 | 2026-08-19 11:01 | 2026-08-19 11:01 | Finished
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Milling (FR4-02) | FALSE | 763 | 404 | 2026-09-11 09:22 | 2026-09-14 10:06 | In Progress
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 763 | 172 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 763 | 86 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-05 17:05 | __export__.mrp_production_7739_ac3d7db5 | TRUE | 2026-08-19 11:05 | Normal | [4022-656-92231] Exhaust fw bridge 1980 | 14980 | 126 | Pcs | TBRM /MO/02362 | OP/14073 - S04833 | 2026-08-19 11:05 | 2026-09-16 11:05 | In Progress | 2026-10-06 02:00 | [5601-0000-0015] ALU 6082 T6 plat 80x10 | __export__.product_product_14157_cfe0fb31 | 18000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 3615 | 141 | 2026-08-19 11:05 | 2026-08-19 13:56 | In Progress
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling (FR3_02) | FALSE | 3615 | 1098 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodising & Cleaning Surface Grade 4 | FALSE | 3615 | 2250 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 3615 | 126 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-21 09:04 | __export__.mrp_production_7611_d448c526 | TRUE | 2026-08-19 11:09 | Normal | [4022-671-49061] Bpam front 1 | 14988 | 152 | Pcs | TBRM /MO/02308 | OP/14104 - S04781 | 2026-08-19 11:09 | 2026-09-09 11:09 | In Progress | 2026-10-05 02:00 | [5601-0000-0008] ALU 6082 T6 plat 40x20 | __export__.product_product_14150_a5d5cc8b | 16681.7 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 2779 | 167 | 2026-08-19 11:09 | 2026-08-19 11:09 | Finished
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR3_01) | FALSE | 2779 | 1610 | 2026-09-10 12:36 | 2026-09-10 12:36 | Finished
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling (FR3_01) | FALSE | 2779 | 850 | 2026-09-10 12:36 | 2026-09-14 12:46 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 2779 | 152 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-05 17:19 | __export__.mrp_production_7741_29c5a051 | TRUE | 2026-08-20 12:45 | Normal | [M0216-01-363-B] nul-graden arretsegment | 15042 | 46 | Pcs | TBRM /MO/02364 | OP/14119 | 2026-08-20 12:45 | 2026-09-15 08:30 | In Progress | 2026-09-02 12:00 | [5603-0000-0018] STAAL s235jr wgw plat 70x20 | __export__.product_product_15125_1f1d8f66 | 24400 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 4231 | 105 | 2026-08-19 10:56 | 2026-08-19 10:56 | Finished
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling (FR3_02) | FALSE | 4231 | 360 | 2026-08-20 12:45 | 2026-08-21 10:15 | To Do
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling (FR3_02) | FALSE | 4231 | 1378 | 2026-08-26 08:13 | 2026-08-31 09:11 | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4231 | 92 | 2026-08-31 09:11 | 2026-08-31 10:43 | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 4231 | 2250 | 2026-09-08 08:14 | 2026-09-14 16:14 | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4231 | 46 | 2026-09-14 16:14 | 2026-09-15 08:30 | Blocked
TBRM Machining B.V. | Available | 2026-07-29 10:04 | __export__.mrp_production_7728_33c6fb58 | TRUE | 2026-08-20 13:20 | Normal | [4022-333-13805] dr pnt cilinder | 14917 | 226 | Pcs | TBRM /MO/02357 |  | 2026-08-20 13:20 | 2026-09-22 15:16 | In Progress |  | [5603-0000-0014] STAAL 11SMn30+C/9SMn28K blank vk 50 | __export__.product_product_15121_d260132d | 3000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 6281 | 265 | 2026-08-19 10:55 | 2026-08-19 10:55 | Finished
[20 empty] | UMC750SS-2 | __export__.mrp_workcenter_62_468a38e5 | Milling (FR5_01) | FALSE | 6281 | 2772 | 2026-09-10 12:37 | 2026-09-10 12:37 | In Progress
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 6281 | 542 | 2026-08-31 12:50 | 2026-09-01 13:52 | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 6281 | 2250 | 2026-09-14 16:14 | 2026-09-21 15:44 | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 6281 | 226 | 2026-09-21 15:44 | 2026-09-22 11:00 | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 6281 | 226 | 2026-09-22 11:00 | 2026-09-22 15:16 | Blocked
TBRM Machining B.V. | Available | 2026-09-10 14:57 | __export__.mrp_production_7913_fa9a279e | FALSE | 2026-09-10 14:57 | Normal | [4022-671-49061] Bpam front 1 | 14988 | 12 | Pcs | TBRM /MO/01830-002 | OP/14104 - S04606 | 2026-08-21 02:00 | 2026-09-11 02:00 | Confirmed | 2026-09-11 02:00 | [5601-0000-0008] ALU 6082 T6 plat 40x20 | __export__.product_product_14150_a5d5cc8b | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 399 | 27 |  |  | Cancelled
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR3_01) | FALSE | 399 | 210 |  |  | Cancelled
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling (FR3_01) | FALSE | 399 | 150 |  |  | To Do
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 399 | 12 |  |  | Blocked
TBRM Machining B.V. | Exp 02/09/2026 | 2026-08-03 09:02 | __export__.mrp_production_7733_4e1717c8 | FALSE | 2026-08-03 09:07 | Normal | [4022.666.20971-TBRM MCH] WTP IM MK6 BRACKET RING | 13691 | 500 | Pcs | TBRM /MO/02255-002 | S04717 | 2026-08-24 02:00 | 2026-09-14 02:00 | Confirmed | 2026-09-14 02:00 | [4022.666.20971ABLaserfileV2] WTP IM MK6 BRACKET RING laser cutted + grinding both sides blank / 4022.666.20971ABLaserfileV2 | __export__.product_product_17402_254f1ca1 | 0 | VF2SS | __export__.mrp_workcenter_60_6593b576 | Picking | FALSE | 16720 | 560 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 16720 | 11660 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning & Packing SG4 | FALSE | 16720 | 4500 |  |  | Blocked
TBRM Machining B.V. | Exp 09/09/2026 | 2026-07-16 13:46 | __export__.mrp_production_7595_a7a474ef | FALSE | 2026-08-21 11:28 | Normal | [4022-451-22801B] RS Lock MF-X Preload Housing | 15540 | 14 | Pcs | TBRM /MO/02302 | S04706 | 2026-08-25 02:00 | 2026-09-15 02:00 | Confirmed | 2026-09-15 02:00 | [5601-0000-0025] ALU 6082 T651 (wgw) gzgd plaat 125x30 | __export__.product_product_14381_aabfdbd5 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | sawing | FALSE | 5269 | 29 |  |  | To Do
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP1 | FALSE | 5269 | 440 |  |  | Blocked
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP2 | FALSE | 5269 | 300 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize RED | FALSE | 5269 | 4500 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-22 15:37 | __export__.mrp_production_7672_51eb241f | TRUE | 2026-08-19 11:02 | Normal | [m05534] Spacer pos 1 | 17395 | 200 | Pcs | TBRM /MO/02315 | S04790 | 2026-08-25 02:00 | 2026-09-09 11:02 | In Progress | 2026-09-15 02:00 | [5601-0000-0179] ALU 6082 T6 plat 150x20 | __export__.product_product_17397_606c4f38 | 30000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 805 | 215 | 2026-08-19 11:02 | 2026-08-19 11:02 | Finished
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling | FALSE | 805 | 590 |  |  | To Do
TBRM Machining B.V. | Available | 2026-07-16 10:40 | __export__.mrp_production_7590_9c5b2965 | TRUE | 2026-09-10 15:12 | Normal | [4022-674-35671] MBI WS LTT SSXY MAN PLUG | 14992 | 46 | Pcs | TBRM /MO/02297 | S04758 | 2026-08-26 02:00 | 2026-09-16 11:03 | In Progress | 2026-09-23 02:00 | [5601-0000-0113] ALU 6082 T6 plat 50x25 | __export__.product_product_15096_693d3e5a | 6000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 3933 | 61 | 2026-08-19 11:03 | 2026-08-19 11:03 | Finished
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Milling (FR5_01) | FALSE | 3933 | 750 | 2026-09-10 12:31 | 2026-09-10 12:31 | Finished
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Milling (FR3_01) | FALSE | 3933 | 780 | 2026-09-10 12:32 | 2026-09-10 15:12 | Finished
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 3933 | 46 | 2026-09-10 15:12 | 2026-09-10 15:12 | Finished
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodising | FALSE | 3933 | 2250 | 2026-09-10 15:12 | 2026-09-17 14:42 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 3933 | 46 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-05 17:12 | __export__.mrp_production_7740_e129fbb8 | FALSE | 2026-08-13 14:13 | Normal | [4022-333-58791] Filterhouder Cu 0.1 | 14921 | 64 | Pcs | TBRM /MO/02363 | OP/14049 - S04837 | 2026-08-28 02:00 | 2026-09-18 02:00 | Confirmed | 2026-09-18 02:00 | [5604-0000-0005] MESSING CuZn40Pb3 plat 16x2 | __export__.product_product_15113_f0f788d6 | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 730 | 64 |  |  | To Do
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4-01) | FALSE | 730 | 282 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 730 | 320 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 730 | 64 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-31 13:09 | __export__.mrp_production_7888_854ab914 | FALSE | 2026-08-31 13:09 | Normal | [4022.632.63021] WTP LOCKING NUT | 7034 | 878 | Pcs | TBRM /MO/01828-004 | S04396 | 2026-08-31 13:09 | 2026-09-21 13:09 | Confirmed | 2026-08-10 14:00 | [5602-0000-0058] RVS 303 (1.4305) wgw geschild rond dia 40 | __export__.product_product_17313_9cdb5eb7 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing - OP1 | FALSE | 2936 | 29 |  |  | Cancelled
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Facing - OP0 | FALSE | 2936 | 300 |  |  | Cancelled
[20 empty] | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing - OP2 | FALSE | 2936 | 29 |  |  | Cancelled
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling | FALSE | 2936 | 328 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning | FALSE | 2936 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-31 13:15 | __export__.mrp_production_7891_80e51730 | FALSE | 2026-08-31 13:15 | Normal | [4022.666.20971-TBRM MCH] WTP IM MK6 BRACKET RING | 13691 | 201 | Pcs | TBRM /MO/02429 |  | 2026-08-31 13:15 | 2026-09-21 13:15 | Confirmed | 2026-07-15 02:00 | [4022.666.20971ABLaserfileV2] WTP IM MK6 BRACKET RING laser cutted + grinding both sides blank / 4022.666.20971ABLaserfileV2 | __export__.product_product_17402_254f1ca1 | 0 | VF2SS | __export__.mrp_workcenter_60_6593b576 | Picking | FALSE | 9484.2 | 261 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 9484.2 | 4723.2 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning & Packing SG4 | FALSE | 9484.2 | 4500 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 11:34 | __export__.mrp_production_7502_1e11fbd9 | TRUE | 2026-09-10 09:22 | Normal | [4022.704.19302] RH RED STATIC STRAIN RELIEF A | 6974 | 124 | Pcs | TBRM /MO/02217 | S04690 | 2026-09-01 02:00 | 2026-09-23 11:03 | In Progress | 2026-10-06 02:00 | [5602-0000-0025] RVS 316L wgw plat 40x15 | __export__.product_product_14192_26c9adbe | 2108 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 7735 | 139 | 2026-08-19 11:03 | 2026-08-19 11:03 | Finished
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Machining OP1 | FALSE | 7735 | 2664 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Machining OP2 | FALSE | 7735 | 308 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivate + Cleaning | FALSE | 7735 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 7735 | 124 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-23 17:05 | __export__.mrp_production_7691_42b2dd71 | TRUE | 2026-08-19 11:04 | Normal | [E05537] Spacer pos 1 | 18608 | 100 | Pcs | TBRM /MO/02326 | S04802 | 2026-09-01 02:00 | 2026-09-09 11:04 | In Progress | 2026-09-22 02:00 | [5601-0000-0183] ALU 6082 T651 (wgw) gzgd plaat 142x142x20 | __export__.product_product_17606_b972fa2d | 100 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 590 | 100 | 2026-08-19 11:04 | 2026-08-19 11:04 | Finished
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling | FALSE | 590 | 390 |  |  | To Do
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | Quality Check | FALSE | 590 | 100 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-04-23 12:35 | __export__.mrp_production_6205_8e927596 | TRUE | 2026-09-08 12:05 | Normal | [00385-00-274-D] Filling block | 14888 | 616 | Pcs | TBRM /MO/01668 | OP/14112 | 2026-09-04 20:11 | 2026-09-09 14:30 | In Progress | 2026-05-14 12:00 | [5601-0000-0010] ALU 6082 T6 vk 70 | __export__.product_product_14152_7df8680e | 20454.55 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 8701 | 631 | 2026-06-10 15:52 | 2026-06-10 15:52 | Finished
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | OP1 | FALSE | 8701 | 4890 | 2026-08-19 10:33 | 2026-08-19 10:33 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 8701 | 1890 | 2026-09-04 20:11 | 2026-09-08 12:01 | Finished
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Benchwork | FALSE | 8701 | 690 | 2026-09-04 20:11 | 2026-09-08 10:16 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging | FALSE | 8701 | 600 | 2026-09-08 12:30 | 2026-09-09 14:30 | To Do
TBRM Machining B.V. | Available | 2026-06-02 09:21 | __export__.mrp_production_6443_1af444bd | TRUE | 2026-09-10 09:23 | Normal | [4022.622.61092] RH RED GRIPPER CABLE COVER | 7366 | 68 | Pcs | TBRM /MO/01756 | S04501 | 2026-09-07 02:00 | 2026-10-14 11:04 | In Progress | 2026-11-02 01:00 | [5602-0000-0031] RVS 316L wgw plat 80x20 | __export__.product_product_14485_407ff3ad | 1700 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 15057 | 83 | 2026-08-19 11:04 | 2026-08-19 11:04 | Finished
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Machining PO1 (M5-04) | FALSE | 15057 | 1420 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Machining OP2 | FALSE | 15057 | 2236 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Electropolishing | FALSE | 15057 | 2250 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Engraving | FALSE | 15057 | 2250 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning Grade 1 | FALSE | 15057 | 6750 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 15057 | 68 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-21 09:01 | __export__.mrp_production_7610_4dd9b2ac | TRUE | 2026-08-19 11:04 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 15022 | 300 | Pcs | TBRM /MO/02307 | S04779 | 2026-09-07 02:00 | 2026-10-07 11:04 | In Progress | 2026-10-26 01:00 | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 12903.23 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 19395 | 315 | 2026-08-19 11:04 | 2026-08-19 11:04 | Finished
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Milling (FR4-02) | FALSE | 19395 | 7590 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 19395 | 1290 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 19395 | 900 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Painting | FALSE | 19395 | 9000 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 19395 | 300 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-04 13:28 | __export__.mrp_production_7895_06743acd | FALSE | 2026-09-07 15:16 | Normal | [7005-2580-0007] Support block / 07201506 v02-00 - Drawing in RED | 16269 | 5 | Pcs | TBRM /MO/02215-002 | S04689 | 2026-09-07 02:00 | 2026-09-28 02:00 | Confirmed | 2026-09-28 02:00 | [5602-0000-0052] RVS 304/304L wgw plat 120x60 | __export__.product_product_16617_20cbe9bc | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 1085 | 20 |  |  | Cancelled
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling - OP1 | FALSE | 1085 | 840 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling - OP2 | FALSE | 1085 | 225 |  |  | Blocked
TBRM Machining B.V. | Not Available | 2026-09-07 10:33 | __export__.mrp_production_7896_78a23dcc | FALSE | 2026-09-09 12:00 | Normal | [7005-2580-0001] Stroke Limiter Plate ZY-L V01-02-B / 26223910 | 16253 | 9 | Pcs | TBRM /MO/02432 | Manual Replenishment | 2026-09-07 10:33 | 2026-09-28 10:33 | Confirmed | 2027-03-02 10:33 | [5601-0000-0029] ALU 6082 T651 (wgw) gzgd plaat 50x50 | __export__.product_product_14385_d0af5b73 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Zagen | FALSE | 2523 | 24 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2523 | 249 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize | FALSE | 2523 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-07 10:41 | __export__.mrp_production_7897_79d03207 | FALSE | 2026-09-07 10:41 | Normal | [7005-2580-0002] Stroke Limiter Plate ZY-R V01-02-B / 26223909 | 16254 | 9 | Pcs | TBRM /MO/02433 | Manual Replenishment | 2026-09-07 10:41 | 2026-09-28 10:41 | Confirmed | 2026-09-28 10:41 | [5601-0000-0029] ALU 6082 T651 (wgw) gzgd plaat 50x50 | __export__.product_product_14385_d0af5b73 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  | FALSE | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  | FALSE | 105 | 90 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-07 10:43 | __export__.mrp_production_7898_77b3c1b2 | FALSE | 2026-09-07 10:43 | Normal | [7005-2580-0003] Stroke Limiter Plate RX-R V02-02-B / 26223908 | 16255 | 9 | Pcs | TBRM /MO/02434 | Manual Replenishment | 2026-09-07 10:43 | 2026-09-28 10:43 | Confirmed | 2026-09-28 10:43 | [5601-0000-0023] ALU 6082 T651 (wgw) gzgd plaat 75x30 | __export__.product_product_14379_b8846587 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Zagen | FALSE | 2514 | 24 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2514 | 240 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize | FALSE | 2514 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-07 10:45 | __export__.mrp_production_7899_69958964 | FALSE | 2026-09-07 10:45 | Normal | [7005-2580-0004] Stroke Limiter Plate RX-L V02-02-A / 26223907 | 16256 | 9 | Pcs | TBRM /MO/02435 | Manual Replenishment | 2026-09-07 10:45 | 2026-09-28 10:45 | Confirmed | 2026-09-28 10:45 | [5601-0000-0023] ALU 6082 T651 (wgw) gzgd plaat 75x30 | __export__.product_product_14379_b8846587 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Zagen | FALSE | 2514 | 24 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 2514 | 240 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize | FALSE | 2514 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-08 14:36 | __export__.mrp_production_7905_71b9de52 | FALSE | 2026-09-08 14:36 | Normal | [7001-2580-0022] HOLDER CREDIT CARD / FM / FM-02-007-C | 17772 | 3 | Pcs | TBRM /MO/02438 |  | 2026-09-08 14:36 | 2026-09-29 14:36 | Confirmed |  | [5601-0000-0035] ALU 6082 T651 (wgw) gzgd plaat 200x50 | __export__.product_product_14391_7229d07d | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2661 | 16 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling OP1 | FALSE | 2661 | 148 |  |  | Blocked
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling OP2 | FALSE | 2661 | 247 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2661 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-08 14:38 | __export__.mrp_production_7906_76f85a9c | FALSE | 2026-09-08 14:38 | Normal | [7001-2580-0037] SA Lens Mount / FM / FM-02-020-B | 17787 | 3 | Pcs | TBRM /MO/02439 |  | 2026-09-08 14:37 | 2026-09-29 14:37 | Confirmed |  | [5601-0000-0024] ALU 6082 T651 (wgw) gzgd plaat 100x30 | __export__.product_product_14380_4f95a69e | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2428 | 16 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 2428 | 162 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2428 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-08 14:38 | __export__.mrp_production_7907_0394c07d | FALSE | 2026-09-08 14:38 | Normal | [7001-2580-0020] Monitor Support 2 / FM / FM-02-045-B | 17770 | 6 | Pcs | TBRM /MO/02440 |  | 2026-09-08 14:38 | 2026-09-29 14:38 | Confirmed |  | [5601-0000-0036] ALU 6082 T651 (wgw) gzgd plaat 200x15 | __export__.product_product_14392_8b21e679 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 2340.67 | 16 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 2340.67 | 74.67 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize black | FALSE | 2340.67 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-16 10:40 | __export__.mrp_production_7589_1463ab54 | FALSE | 2026-09-07 14:34 | Normal | [4022-666-3837-1] LSPH Bellow Clamp | 14985 | 212 | Pcs | TBRM /MO/02296 | S04758 | 2026-09-10 02:00 | 2026-10-08 02:00 | Confirmed | 2026-10-08 02:00 | [5990-0000-0017] LSPH Bellow Clamp cutout | __export__.product_product_15112_c44437c2 | 0 | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 2512 | 1150 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 2512 | 726 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 2512 | 424 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 2512 | 212 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-08 12:24 | __export__.mrp_production_7902_8f5cd62c | FALSE | 2026-09-10 15:56 | Normal | [4022-656-74553] Assy support guide FW 1980 | 14977 | 50 | Pcs | TBRM /MO/02436 | S04954 | 2026-09-10 02:00 | 2026-10-01 02:00 | Confirmed | 2026-10-01 02:00 |  |  |  | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking (customer supplied) | FALSE | 1540 | 50 |  |  | To Do
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR5_01) | FALSE | 1540 | 1340 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 1540 | 100 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 1540 | 50 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-05-11 13:11 | __export__.mrp_production_6301_619807e1 | TRUE | 2026-09-10 12:30 | Normal | [00385-00-113A] Tensioner plate | 14887 | 700 | Pcs | TBRM /MO/01730 | OP/14107 | 2026-09-10 12:30 | 2026-10-08 12:30 | In Progress | 2026-06-08 12:00 | [5990-0000-0018] Tensioner Plate cutout | __export__.product_product_15131_791d3010 | 700 | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | Pre-cutted, picking only | FALSE | 14180 | 790 | 2026-09-10 12:30 | 2026-09-10 12:30 | Finished
[20 empty] | FR4_02 | __export__.mrp_workcenter_57_6faf5319 | OP1 | FALSE | 14180 | 10590 | 2026-09-10 12:30 | 2026-09-29 18:00 | In Progress
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 14180 | 2100 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 14180 | 700 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-09 11:27 | __export__.mrp_production_7517_eab0fb08 | TRUE | 2026-09-10 12:36 | Normal | [4022-671-49061] Bpam front 1 | 14988 | 54 | Pcs | TBRM /MO/02232 | OP/14104 - S04698 | 2026-09-10 12:36 | 2026-09-11 08:54 | In Progress | 2026-09-17 02:00 | [5601-0000-0008] ALU 6082 T6 plat 40x20 | __export__.product_product_14150_a5d5cc8b | 6000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 1113 | 69 | 2026-08-19 11:03 | 2026-08-19 11:03 | Finished
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | Milling (FR3_01) | FALSE | 1113 | 630 | 2026-09-10 12:35 | 2026-09-10 12:35 | Finished
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling (FR3_01) | FALSE | 1113 | 360 | 2026-09-10 12:36 | 2026-09-10 18:36 | In Progress
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 1113 | 54 | 2026-09-11 08:00 | 2026-09-11 08:54 | Blocked
TBRM Machining B.V. | Available | 2026-07-21 14:33 | __export__.mrp_production_7614_32f48c3b | TRUE | 2026-09-11 11:40 | Normal | [00385-00-346-A] Plint fixing strip right | 14892 | 279 | Pcs | TBRM /MO/02310 |  | 2026-09-11 11:40 | 2026-10-06 13:37 | In Progress |  | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 12093.99 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Automatic Sawing (ZGN_01) | FALSE | 6909 | 294 | 2026-07-21 14:33 | 2026-07-21 14:33 | Finished
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | OP1 | FALSE | 6909 | 2322 | 2026-07-21 14:33 | 2026-07-21 14:33 | Finished
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | OP2 | FALSE | 6909 | 1206 | 2026-09-11 11:40 | 2026-09-16 09:46 | To Do
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 6909 | 558 | 2026-09-16 09:46 | 2026-09-17 11:04 | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 6909 | 2250 | 2026-09-29 08:58 | 2026-10-06 08:28 | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 6909 | 279 | 2026-10-06 08:28 | 2026-10-06 13:37 | Blocked
TBRM Machining B.V. | Available | 2026-07-21 14:35 | __export__.mrp_production_7615_4046e64b | TRUE | 2026-09-11 13:12 | Normal | [00385-00-321-A] Plint fixing strip left | 14890 | 714 | Pcs | TBRM /MO/02311 |  | 2026-09-11 13:12 | 2026-10-15 08:18 | In Progress |  | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 30000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 13869 | 729 | 2026-08-19 10:50 | 2026-08-19 10:51 | Finished
[20 empty] | FR5_01 | __export__.mrp_workcenter_59_d6deab7b | OP1 | FALSE | 13869 | 5802 | 2026-09-11 13:12 | 2026-09-30 11:24 | To Do
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | OP2 | FALSE | 13869 | 2946 | 2026-09-23 08:00 | 2026-09-28 18:06 | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 13869 | 1428 | 2026-10-01 11:06 | 2026-10-06 13:24 | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivating | FALSE | 13869 | 2250 | 2026-10-06 13:24 | 2026-10-13 12:54 | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 13869 | 714 | 2026-10-13 12:54 | 2026-10-15 08:18 | Blocked
TBRM Machining B.V. | Available | 2026-07-28 16:14 | __export__.mrp_production_7724_4095beb0 | TRUE | 2026-08-19 11:09 | Normal | [4022.632.63021] WTP LOCKING NUT | 7034 | 1600 | Pcs | TBRM /MO/02354 | S04825 | 2026-09-14 02:00 | 2026-09-09 11:09 | In Progress | 2026-10-05 02:00 | [5602-0000-0058] RVS 303 (1.4305) wgw geschild rond dia 40 | __export__.product_product_17313_9cdb5eb7 | 24659.4 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing - OP1 | FALSE | 3276 | 39 | 2026-08-19 11:09 | 2026-08-19 11:09 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Facing - OP0 | FALSE | 3276 | 450 |  |  | To Do
[20 empty] | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing - OP2 | FALSE | 3276 | 39 |  |  | Blocked
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling | FALSE | 3276 | 498 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning | FALSE | 3276 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-06 16:36 | __export__.mrp_production_7747_63c937d1 | FALSE | 2026-09-03 18:11 | Normal | [7005-2580-0014] Backplate V01-00 / NFI / 27244701 | 17992 | 5 | Pcs | TBRM /MO/02367 | S04845 | 2026-09-14 02:00 | 2026-10-05 02:00 | Confirmed | 2026-10-05 02:00 | [5601-0000-0225] ALU 5083 gegoten gefreesd 800x500x15mm | __export__.product_product_19129_c3f22491 | 0 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 3905 | 5 |  |  | To Do
[20 empty] | FR3_02 | __export__.mrp_workcenter_55_15609e22 | Milling | FALSE | 3905 | 1650 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize clear | FALSE | 3905 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-06 16:36 | __export__.mrp_production_7748_9688d8c1 | FALSE | 2026-09-03 18:11 | Normal | [7005-2580-0015] Baseplate V01-00 / NFI / 27244702 | 17993 | 5 | Pcs | TBRM /MO/02368 | S04845 | 2026-09-14 02:00 | 2026-10-05 02:00 | Confirmed | 2026-10-05 02:00 | [5601-0000-0175] ALU 5083 (O3) gegoten 6 zijdig gezaagd 520x250x45 | __export__.product_product_17008_b36cccae | 0 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 3040 | 5 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 3040 | 785 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize (clear) | FALSE | 3040 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-06 16:36 | __export__.mrp_production_7750_7174a83f | FALSE | 2026-09-03 18:11 | Normal | [7005-2580-0010] Cylinder bracket V01-00 / NFI / 27244703 | 16360 | 4 | Pcs | TBRM /MO/02370 | S04845 | 2026-09-14 02:00 | 2026-10-05 02:00 | Confirmed | 2026-10-05 02:00 | [5601-0000-0176] ALU 5083 (O3) gegoten 6 zijdig gezaagd 295x250x30 | __export__.product_product_17009_eae1abf8 | 0 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 2352 | 1 |  |  | To Do
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | milling | FALSE | 2352 | 101 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize (clear) | FALSE | 2352 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-07 14:58 | __export__.mrp_production_7204_644ef9b4 | FALSE | 2026-07-07 14:58 | Normal | [4022-335-19371] Filterhouder Ni 0.02mm | 16241 | 60 | Pcs | TBRM /MO/01939 | S04672 | 2026-09-15 02:00 | 2026-10-06 02:00 | Confirmed | 2026-10-06 02:00 | [5604-0000-0005] MESSING CuZn40Pb3 plat 16x2 | __export__.product_product_15113_f0f788d6 | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 691 | 60 |  |  | To Do
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4-01) | FALSE | 691 | 270 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 691 | 300 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 691 | 61 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-08 11:34 | __export__.mrp_production_7501_149d84b1 | TRUE | 2026-09-10 09:23 | Normal | [4022.684.32042] RH RED DYNAMIC STRAIN RELIEF B | 7363 | 80 | Pcs | TBRM /MO/02216 | S04690 | 2026-09-15 02:00 | 2026-09-23 11:09 | In Progress | 2026-10-20 02:00 | [5602-0000-0032] RVS 316L wgw vk 30 | __export__.product_product_14486_67682100 | 800 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 8576.33 | 96.33 | 2026-08-19 11:09 | 2026-08-19 11:09 | Finished
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Machining (M5-04) | FALSE | 8576.33 | 3900 |  |  | To Do
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivate + Cleaning | FALSE | 8576.33 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 8576.33 | 80 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-08 12:28 | __export__.mrp_production_7903_cbbe0eed | FALSE | 2026-09-10 15:58 | Normal | [M.459800425070/1] Spring brake suspension | 15040 | 459 | Pcs | TBRM /MO/02437 | S04956 | 2026-09-15 02:00 | 2026-10-06 02:00 | Confirmed | 2026-10-06 02:00 |  |  |  | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Picking (UITG_M) | FALSE | 2016 | 90 |  |  | To Do
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4_02) | FALSE | 2016 | 1926 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-09 11:41 | __export__.mrp_production_7518_26f78d7f | TRUE | 2026-08-21 10:30 | Normal | [4512-127-05186B] Anschlag | 15017 | 967 | Pcs | TBRM /MO/02233 | OP/14097 - S04700 | 2026-09-21 02:00 | 2026-09-09 11:09 | In Progress | 2026-10-12 02:00 | [5990-0000-0012] Ensat-SBS zelfsn.draadbus M6x12 Stl.gh. | __export__.product_product_15107_d0c7b2b3 | 967 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 7841 | 982 | 2026-08-19 11:09 | 2026-08-19 11:09 | Finished
[17 empty] | [5601-0000-0008] ALU 6082 T6 plat 40x20 | __export__.product_product_14150_a5d5cc8b | 41152.3
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling (FR4-01) | FALSE | 7841 | 4925 |  |  | To Do
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 7841 | 967 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 7841 | 967 |  |  | Blocked
TBRM Machining B.V. | Exp 09/09/2026 | 2026-08-19 17:08 | __export__.mrp_production_7790_eac47069 | FALSE | 2026-08-19 17:10 | Normal | [4022.684.28962] RS C+H DYN ATTACH PLT RH SIDE / CLS | 18348 | 1 | Pcs | TBRM /MO/02376 | S04872 | 2026-09-23 02:00 | 2026-10-14 02:00 | Confirmed | 2026-10-14 02:00 | [5601-0000-0208] ALU 6082 T651 (wgw) gzgd plaat 320x120x45 | __export__.product_product_18743_a009a4c2 | 0 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 9336 | 1 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | OP1 | FALSE | 9336 | 335 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Nickel Plating | FALSE | 9336 | 4500 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning | FALSE | 9336 | 4500 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-06 16:36 | __export__.mrp_production_7746_16c74a56 | FALSE | 2026-08-06 16:55 | Normal | [7005-2580-0017] GP Z-Adjustment Lever V02-01 / 26241001 | 18142 | 18 | Pcs | TBRM /MO/02366 | S04845 | 2026-09-24 02:00 | 2026-10-15 02:00 | Confirmed | 2026-10-15 02:00 | [5602-0000-0051] RVS 304/304L wgw plat 90x20 | __export__.product_product_16616_0f026687 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 4413 | 33 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 4413 | 2130 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivation | FALSE | 4413 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-06 16:36 | __export__.mrp_production_7749_e2513146 | TRUE | 2026-08-19 11:10 | Normal | [7005-2580-0005] Single Rail V01-00-A (IGUS / WSQ-06S) / NFI / 26224401 | 16257 | 30 | Pcs | TBRM /MO/02369 | S04845 | 2026-09-24 02:00 | 2026-09-09 11:10 | In Progress | 2026-10-15 02:00 | Single rail WSQ - not drilled / IGUS / WSQ-06S | __export__.product_product_16262_062fd235 | 2 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Sawing | FALSE | 74 | 2 | 2026-08-19 11:10 | 2026-08-19 11:12 | In Progress
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | Milling | FALSE | 74 | 72 |  |  | Blocked
TBRM Machining B.V. |  | 2026-09-02 09:02 | __export__.mrp_production_7893_e21f3ab2 | FALSE | 2026-09-02 09:02 | Normal | [P03421A] Cap Motor Housing M3 / VDM / P03421A | 20051 | 2 | Pcs | TBRM /MO/02430 | S04936 | 2026-09-28 07:00 | 2026-09-28 09:30 | Draft | 2026-09-28 08:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-09-02 09:02 | __export__.mrp_production_7894_d4db6bc1 | FALSE | 2026-09-02 09:02 | Normal | [P03422] Frameplate T6 gearbox 40mm flange / VDM / P03422 | 20052 | 5 | Pcs | TBRM /MO/02431 | S04936 | 2026-09-28 07:00 | 2026-09-28 09:30 | Draft | 2026-09-28 08:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. | Available | 2026-07-07 23:26 | __export__.mrp_production_7209_f5d9253c | TRUE | 2026-09-10 09:29 | Normal | [4022.704.19282] RH RED GRIPPER BODY | 14210 | 60 | Pcs | TBRM /MO/01942 | S04680 | 2026-10-02 02:00 | 2026-09-07 11:31 | In Progress | 2026-10-23 02:00 | [5602-0000-0060] RVS 316/316L 1 richting gzgd plaat 210x105x30 (tol. -0/+3mm) | __export__.product_product_17381_95528666 | 60 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 45612.13 | 60 | 2026-08-17 11:31 | 2026-08-17 11:31 | Finished
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anneal | FALSE | 45612.13 | 7092.13 | 2026-08-17 11:31 | 2026-09-07 16:13 | Finished
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling - OP1/2 | FALSE | 45612.13 | 3690 |  |  | Blocked
[20 empty] | UMC750-3 | __export__.mrp_workcenter_83_95c50e96 | Milling - OP3/4 | FALSE | 45612.13 | 28860 |  |  | Blocked
[20 empty] | UMC400 | __export__.mrp_workcenter_84_05c538b3 | Milling - OP5 | FALSE | 45612.13 | 3660 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Passivation, Bake-out, Cleaning and Packing according to drawing | FALSE | 45612.13 | 2250 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-09 14:07 | __export__.mrp_production_7910_19a04462 | FALSE | 2026-09-10 16:00 | Normal | [P183614A] IQS PCBA MOUNT | 19338 | 12 | Pcs | TBRM /MO/02443 | S04961 | 2026-10-02 02:00 | 2026-10-23 02:00 | Confirmed | 2026-10-23 02:00 | [5601-0000-0036] ALU 6082 T651 (wgw) gzgd plaat 200x15 | __export__.product_product_14392_8b21e679 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing | FALSE | 257 | 17 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP1 | FALSE | 257 | 120 |  |  | Blocked
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 257 | 120 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-13 09:58 | __export__.mrp_production_7762_fc32a349 | FALSE | 2026-08-13 16:38 | Normal | [4512-127-05186B] Anschlag | 15017 | 1000 | Pcs | TBRM /MO/02371 | OP/14097 - S04849 | 2026-10-05 02:00 | 2026-10-26 01:00 | Confirmed | 2026-10-26 01:00 | [5990-0000-0012] Ensat-SBS zelfsn.draadbus M6x12 Stl.gh. | __export__.product_product_15107_d0c7b2b3 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Material prep (ZGN_01) | FALSE | 8105 | 1015 |  |  | To Do
[17 empty] | [5601-0000-0008] ALU 6082 T6 plat 40x20 | __export__.product_product_14150_a5d5cc8b | 0
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling (FR4-01) | FALSE | 8105 | 5090 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 8105 | 1000 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 8105 | 1000 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-08-14 13:58 | __export__.mrp_production_7764_ebe57deb | FALSE | 2026-08-14 13:58 | Normal | [4022-335-17991] Filterh. Cu0.2 Ni0.02 | 14922 | 35 | Pcs | TBRM /MO/02373 | S04857 | 2026-10-07 02:00 | 2026-10-28 01:00 | Confirmed | 2026-10-28 01:00 | [5604-0000-0005] MESSING CuZn40Pb3 plat 16x2 | __export__.product_product_15113_f0f788d6 | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 440 | 35 |  |  | To Do
[20 empty] | FR4_01 | __export__.mrp_workcenter_56_d6637dea | Milling (FR4-01) | FALSE | 440 | 195 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 440 | 175 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 440 | 35 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 13:33 | __export__.mrp_production_7085_77271653 | FALSE | 2026-06-30 13:33 | Normal | [BD50-5085-007-C] bracket | 15031 | 62 | Pcs | TBRM /MO/01832 | S04610 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 5272 | 62 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 5272 | 462 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5272 | 124 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5272 | 62 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 5272 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5272 | 62 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 13:37 | __export__.mrp_production_7086_3f3f3a3d | FALSE | 2026-06-30 13:37 | Normal | [BD50-5085-007-C] bracket | 15031 | 30 | Pcs | TBRM /MO/01833 | S04612 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 4920 | 30 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 4920 | 270 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4920 | 60 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4920 | 30 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 4920 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4920 | 30 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 13:40 | __export__.mrp_production_7087_3703c654 | FALSE | 2026-06-30 13:40 | Normal | [BD50-5085-009-C] bracket | 15032 | 57 | Pcs | TBRM /MO/01834 | S04614 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 5217 | 57 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 5217 | 432 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5217 | 114 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5217 | 57 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 5217 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5217 | 57 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 13:43 | __export__.mrp_production_7088_c4ef1e05 | FALSE | 2026-06-30 13:43 | Normal | [BD50-5085-009-C] bracket | 15032 | 30 | Pcs | TBRM /MO/01835 | S04616 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 4920 | 30 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 4920 | 270 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4920 | 60 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4920 | 30 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 4920 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4920 | 30 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 13:46 | __export__.mrp_production_7089_d51ed5a1 | FALSE | 2026-06-30 13:46 | Normal | [BD50-5085-011-C] bracket | 15033 | 20 | Pcs | TBRM /MO/01836 | S04618 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 4810 | 20 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 4810 | 210 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4810 | 40 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4810 | 20 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 4810 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4810 | 20 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 13:50 | __export__.mrp_production_7090_cf4cbf38 | FALSE | 2026-06-30 13:50 | Normal | [BD50-5085-011-C] bracket | 15033 | 50 | Pcs | TBRM /MO/01837 | S04620 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 5140 | 50 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 5140 | 390 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5140 | 100 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5140 | 50 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 5140 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5140 | 50 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 14:19 | __export__.mrp_production_7093_4e69d2cc | FALSE | 2026-06-30 14:19 | Normal | [BD50-5075-011-E] bracket | 15028 | 52 | Pcs | TBRM /MO/01840 | S04628 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 5058 | 52 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 5058 | 298 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5058 | 104 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5058 | 52 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 5058 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5058 | 52 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 14:22 | __export__.mrp_production_7094_5fd6a028 | FALSE | 2026-06-30 14:22 | Normal | [BD50-5075-013F] bracket | 15029 | 50 | Pcs | TBRM /MO/01841 | S04630 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 5140 | 50 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 5140 | 390 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5140 | 100 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5140 | 50 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 5140 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5140 | 50 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 14:24 | __export__.mrp_production_7095_932ac3aa | FALSE | 2026-06-30 14:24 | Normal | [BD50-5075-013F] bracket | 15029 | 20 | Pcs | TBRM /MO/01842 | S04632 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 4810 | 20 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 4810 | 210 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4810 | 40 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4810 | 20 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 4810 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4810 | 20 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 14:28 | __export__.mrp_production_7096_98ba3320 | FALSE | 2026-06-30 14:28 | Normal | [BD50-5075-015F] bracket | 15030 | 43 | Pcs | TBRM /MO/01843 | S04634 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 5063 | 43 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 5063 | 348 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5063 | 86 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5063 | 43 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 5063 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 5063 | 43 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 14:39 | __export__.mrp_production_7097_07647ff1 | FALSE | 2026-06-30 14:39 | Normal | [BD50-5075-015F] bracket | 15030 | 20 | Pcs | TBRM /MO/01844 | S04636 | 2026-10-08 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 4810 | 20 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 4810 | 210 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4810 | 40 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4810 | 20 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 4810 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4810 | 20 |  |  | Blocked
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7855_92242b70 | FALSE | 2026-08-26 19:47 | Normal | [7001-2680-0002] PFS Edge Exclusion Block / FM / FM1022-M00042-A | 19969 | 6 | Pcs | TBRM /MO/02411 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7856_d1a63f41 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00001-A] PFS Top Plate / FM | 19975 | 6 | Pcs | TBRM /MO/02412 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7857_7d64eea4 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00002-A] PFS Bottom Plate / FM | 19983 | 6 | Pcs | TBRM /MO/02413 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7858_a415c3a5 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00003-A] PFS Side Plate CS / FM | 19986 | 6 | Pcs | TBRM /MO/02414 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7859_0c545a25 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00004-A] PFS Side Plate LS / FM | 19987 | 6 | Pcs | TBRM /MO/02415 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7860_cb5dcca0 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00026-B] 2.1 Tilting Mirror Block / FM | 19997 | 6 | Pcs | TBRM /MO/02416 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7861_c9343d98 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00014-A] Tilting mirror mount / FM | 19999 | 6 | Pcs | TBRM /MO/02417 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7862_74cbd59a | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00017-A] PFS Fixed mirror Holder LS / FM | 20000 | 6 | Pcs | TBRM /MO/02418 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7863_4e35ed8f | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00020-A] PFS Upper Mirror Holder CS / FM | 20003 | 6 | Pcs | TBRM /MO/02419 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7864_c9cf2b00 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00021-A] PFS Upper Mirror Holder LS / FM | 20004 | 6 | Pcs | TBRM /MO/02420 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7865_18876198 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00047-A] PFS Camera Block / FM | 20005 | 6 | Pcs | TBRM /MO/02421 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7866_d7919b3b | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00006-B] PFS Lens Housing / FM | 20006 | 6 | Pcs | TBRM /MO/02422 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7867_56faba31 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00031-A] PFS LED Insulator / FM | 20007 | 6 | Pcs | TBRM /MO/02423 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7868_f924c737 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-C00003-A] PFS Add holes HS / FM | 20008 | 6 | Pcs | TBRM /MO/02424 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7869_f48c73fd | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00053-A] PFS Wafer Holder Body Ambient / FM | 20009 | 6 | Pcs | TBRM /MO/02425 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7870_70c44f55 | FALSE | 2026-08-26 19:47 | Normal | [FM1022-M00054-A] PFS Spring Limiter POM / FM | 20010 | 6 | Pcs | TBRM /MO/02426 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-08-26 19:47 | __export__.mrp_production_7871_4a89427f | FALSE | 2026-08-26 19:47 | Normal | [FM0001-M00006-B] GEB Baseplate / FM | 20011 | 6 | Pcs | TBRM /MO/02427 | S04922 | 2026-10-14 18:00 | 2026-10-15 09:30 | Draft | 2026-10-14 19:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. | Available | 2026-08-25 10:39 | __export__.mrp_production_7819_35d26c75 | TRUE | 2026-09-03 09:10 | Normal | [4022-451-22801B] RS Lock MF-X Preload Housing | 15540 | 16 | Pcs | TBRM /MO/02379 | S04885 | 2026-10-16 02:00 | 2026-11-06 01:00 | In Progress | 2026-11-06 01:00 | [5601-0000-0025] ALU 6082 T651 (wgw) gzgd plaat 125x30 | __export__.product_product_14381_aabfdbd5 | 1680 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | sawing | FALSE | 5351 | 31 |  |  | To Do
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP1 | FALSE | 5351 | 490 |  |  | Blocked
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP2 | FALSE | 5351 | 330 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize RED | FALSE | 5351 | 4500 | 2026-09-03 09:10 | 2026-09-17 08:10 | In Progress
TBRM Machining B.V. | Exp 11/09/2026 | 2026-08-25 10:39 | __export__.mrp_production_7820_2e142250 | FALSE | 2026-08-25 10:39 | Normal | [4022-451-22801B] RS Lock MF-X Preload Housing | 15540 | 16 | Pcs | TBRM /MO/02380 | S04885 | 2026-10-16 02:00 | 2026-11-06 01:00 | Confirmed | 2026-11-06 01:00 | [5601-0000-0025] ALU 6082 T651 (wgw) gzgd plaat 125x30 | __export__.product_product_14381_aabfdbd5 | 0 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | sawing | FALSE | 5351 | 31 |  |  | To Do
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP1 | FALSE | 5351 | 490 |  |  | Blocked
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | OP2 | FALSE | 5351 | 330 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize RED | FALSE | 5351 | 4500 |  |  | Blocked
TBRM Machining B.V. | Exp 01/10/2026 | 2026-07-28 16:14 | __export__.mrp_production_7725_9d83dd88 | FALSE | 2026-07-28 16:14 | Normal | [4022.666.20971-TBRM MCH] WTP IM MK6 BRACKET RING | 13691 | 500 | Pcs | TBRM /MO/02355 | S04825 | 2026-10-20 02:00 | 2026-11-10 01:00 | Confirmed | 2026-11-10 01:00 | [4022.666.20971ABLaserfileV2] WTP IM MK6 BRACKET RING laser cutted + grinding both sides blank / 4022.666.20971ABLaserfileV2 | __export__.product_product_17402_254f1ca1 | 0 | VF2SS | __export__.mrp_workcenter_60_6593b576 | Picking | FALSE | 16720 | 560 |  |  | To Do
[20 empty] | UMC750-1 | __export__.mrp_workcenter_61_bcb50df3 | Milling | FALSE | 16720 | 11660 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning & Packing SG4 | FALSE | 16720 | 4500 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-07-28 16:14 | __export__.mrp_production_7726_4df82d87 | TRUE | 2026-08-19 11:11 | Normal | [4022.632.63021] WTP LOCKING NUT | 7034 | 1600 | Pcs | TBRM /MO/02356 | S04825 | 2026-10-20 02:00 | 2026-09-09 11:11 | In Progress | 2026-11-10 01:00 | [5602-0000-0058] RVS 303 (1.4305) wgw geschild rond dia 40 | __export__.product_product_17313_9cdb5eb7 | 24000 | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing - OP1 | FALSE | 3276 | 39 | 2026-08-19 11:11 | 2026-08-19 11:11 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Facing - OP0 | FALSE | 3276 | 450 |  |  | To Do
[20 empty] | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b | Sawing - OP2 | FALSE | 3276 | 39 |  |  | Blocked
[20 empty] | FR5_02 | __export__.mrp_workcenter_58_a525d5b9 | Milling | FALSE | 3276 | 498 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Cleaning | FALSE | 3276 | 2250 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-08-18 13:13 | __export__.mrp_production_7767_dab52ed7 | FALSE | 2026-08-18 13:13 | Normal | [BD50-5075-011-E] bracket | 15028 | 44 | Pcs | TBRM /MO/02375 | S04867 | 2026-10-20 02:00 | 2026-11-24 01:00 | Confirmed | 2026-11-24 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | Material prep (ZGN_02) | FALSE | 4986 | 44 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | Milling (FR3_01) | FALSE | 4986 | 266 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 4986 | 88 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4986 | 44 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromising | FALSE | 4986 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | Packaging (VERP_P) | FALSE | 4986 | 44 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 13:58 | __export__.mrp_production_7091_ee7ba730 | FALSE | 2026-06-30 13:58 | Normal | [BD50-5085-013-C] bracket | 15034 | 55 | Pcs | TBRM /MO/01838 | S04622 | 2026-10-22 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | MP2 - Material preparation - manual sawing (ZGN_02) | FALSE | 5195 | 55 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | M3-01 - Accuwell - 3axis - Manual (FR3_01) | FALSE | 5195 | 420 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5195 | 110 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | PACK - Packaging (VERP_P) | FALSE | 5195 | 55 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromatize | FALSE | 5195 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | PACK - Packaging (VERP_P) | FALSE | 5195 | 55 |  |  | Blocked
TBRM Machining B.V. | Exp 08/09/2026 | 2026-06-30 14:02 | __export__.mrp_production_7092_08ed6ea8 | FALSE | 2026-06-30 14:02 | Normal | [BD50-5085-013-C] bracket | 15034 | 45 | Pcs | TBRM /MO/01839 | S04624 | 2026-10-22 02:00 | 2026-11-12 01:00 | Confirmed | 2026-11-12 01:00 | [5601-0000-0021] ALU 7075 T73511 hoekprofiel 20x16x1.2 | __export__.product_product_14163_0ce7bbea | 0 | Manual saw | __export__.mrp_workcenter_64_95992ef5 | MP2 - Material preparation - manual sawing (ZGN_02) | FALSE | 5085 | 45 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | M3-01 - Accuwell - 3axis - Manual (FR3_01) | FALSE | 5085 | 360 |  |  | Blocked
[20 empty] | Benchwork | __export__.mrp_workcenter_66_9f807a30 | BW - Benchwork (BKW_01) | FALSE | 5085 | 90 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | PACK - Packaging (VERP_P) | FALSE | 5085 | 45 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Chromatize | FALSE | 5085 | 4500 |  |  | Blocked
[20 empty] | Packaging | __export__.mrp_workcenter_67_d1ac8ce6 | PACK - Packaging (VERP_P) | FALSE | 5085 | 45 |  |  | Blocked
TBRM Machining B.V. | Available | 2026-09-10 15:01 | __export__.mrp_production_7914_7a50b497 | TRUE | 2026-09-11 08:36 | Normal | [00002033- 04] ADAPTER PLATE | 19696 | 3 | Pcs | TBRM /MO/02238-002 | S04708 | 2026-10-30 01:00 | 2026-09-11 10:10 | In Progress | 2026-11-20 01:00 | [5601-0000-0151] ALU 5083 gegoten gefreesd gzgd plaat 500x300x20 | __export__.product_product_16160_c3f8ac6c | 1.5 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 158.66 | 2 | 2026-09-11 08:30 | 2026-09-11 08:30 | Finished
[20 empty] | VF2SS | __export__.mrp_workcenter_60_6593b576 | OP1 | FALSE | 158.66 | 63.33 | 2026-09-11 08:35 | 2026-09-11 08:36 | Finished
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 158.66 | 93.33 | 2026-09-11 08:36 | 2026-09-11 10:10 | In Progress
TBRM Machining B.V. | Available | 2026-09-11 17:28 | __export__.mrp_production_7917_b26e078a | FALSE | 2026-09-11 17:29 | Normal | [4022.645.53391] NXE RBI ILLUM TRANSPORT COVER | 19386 | 1 | Pcs | TBRM /MO/02444 | S04965 | 2026-10-30 01:00 | 2026-11-20 01:00 | Confirmed | 2026-11-20 01:00 | [5601-0000-0234] ALU 6082 T651 (wgw) gzgd plaat 360x275x50 | __export__.product_product_19576_4974cf1f | 0 | Pre-Cutted Material | __export__.mrp_workcenter_65_c1e1b939 | Picking | FALSE | 2596 | 1 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP1 | FALSE | 2596 | 135 |  |  | Blocked
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 | OP2 | FALSE | 2596 | 210 |  |  | Blocked
[20 empty] | OUT | __export__.mrp_workcenter_68_8bff6631 | Anodize RED + Clean SG4 | FALSE | 2596 | 2250 |  |  | Blocked
TBRM Machining B.V. |  | 2026-08-25 10:48 | __export__.mrp_production_7822_4c4e9fff | FALSE | 2026-08-25 10:48 | Normal | [7001-2680-0001] SOT Holder Plate / FM / FM2010-M00052-A | 19958 | 20 | Pcs | TBRM /MO/02381 | S04887 | 2027-02-21 11:00 | 2027-02-22 09:30 | Draft | 2027-02-21 12:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-09-09 12:40 | __export__.mrp_production_7908_e1792ea2 | FALSE | 2026-09-09 12:40 | Normal | [7005-2600-0024] MAFM excluding PUT Carrier / NFI / N65262802V01-00 | 20134 | 100 | Pcs | TBRM /MO/02441 | S04959 | 2027-03-08 11:00 | 2027-03-08 13:00 | Draft | 2027-03-08 12:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do
TBRM Machining B.V. |  | 2026-09-09 12:40 | __export__.mrp_production_7909_a9f1155b | FALSE | 2026-09-09 12:40 | Normal | [7005-2600-0025] MAFM holder for realignment / NFI / N24224801V05-00 | 20135 | 2 | Pcs | TBRM /MO/02442 | S04959 | 2027-03-08 11:00 | 2027-03-08 13:00 | Draft | 2027-03-08 12:00 |  |  |  | Automatic Saw | __export__.mrp_workcenter_63_98a7a00b |  |  | 105 | 15 |  |  | To Do
[20 empty] | FR3_01 | __export__.mrp_workcenter_54_3f0243e1 |  |  | 105 | 90 |  |  | To Do