## Sheet1
Company | Component Status | Created on | ID | Its Operations are Planned | Last Updated on | Priority | Product | Product/ID | Quantity To Produce | Product Unit of Measure | Reference | Source | Start | End | State | Deadline | Components/Product | Components/Product/ID | Components/Quantity To Consume | Work Orders/Work Center | Work Orders/Work Center/ID | Work Orders/Bill of Material/Subcontract? | Work Orders/Manufacturing Order/Expected Duration | Work Orders/Expected Duration
TBRM Machining B.V. | Available | 2024-12-06 10:20 | __export__.mrp_production_1064_688e92e1 | FALSE | 2025-03-19 14:39 | Normal | [7005-2480-0090] METROFRAME BODY V02-00-B / 0119073001 | 15889 | 4 | Pcs | TBRM /MO/00305 | S02403 | 2025-02-07 01:00 | 2025-02-28 01:00 | Confirmed | 2025-02-28 01:00 | [5601-0000-0155] ALU 5083 gegoten gzgd plaat 590x460x150 | __export__.product_product_16215_287d75f5 | 0 | M3-02 - Accuway - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | FALSE | 4390 | 1530
[20 empty] | M5-04 - Haas - 5axis - Manual (UMC750SS) | __export__.mrp_workcenter_62_468a38e5 | FALSE | 4390 | 2860
TBRM Machining B.V. | Available | 2024-12-18 12:47 | __export__.mrp_production_1104_d3ae4426 | TRUE | 2025-02-24 14:57 | Normal | [4022-651-55002A] Gpas preamp CB Box + cover assy | 14975 | 27 | Pcs | TBRM /MO/00333 |  | 2025-02-28 11:31 | 2025-03-10 10:13 | Confirmed |  | [5602-0000-0023] RVS 316L wgw vk 80 | __export__.product_product_14190_b2f6cfa7 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 2922 | 42
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 2922 | 1710
[20 empty] | M5-01 - Accuway - 5axis - Conveyor Automation (FR5_01) | __export__.mrp_workcenter_58_a525d5b9 | FALSE | 2922 | 1035
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 2922 | 108
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 2922 | 27
TBRM Machining B.V. |  | 2025-04-09 11:52 | __export__.mrp_production_3892_cec21dc3 | FALSE | 2025-04-09 11:52 | Normal | [7351522] Impact cover-6_rev-0 alleen base voor export-AP214.step | 16989 | 1 | Pcs | TBRM /MO/00620 | S02910 | 2025-03-31 02:00 | 2025-04-14 02:00 | Draft | 2025-04-14 02:00
TBRM Machining B.V. | Available | 2025-08-28 10:59 | __export__.mrp_production_4738_6a3434f8 | FALSE | 2025-08-28 11:05 | Normal | [1508130 B] [Q] excenter housing z | 16893 | 140 | Pcs | TBRM /MO/00710-002 | Manual Replenishment | 2025-04-23 02:00 | 2025-05-14 02:00 | Confirmed | 2025-05-14 13:28 | [5601-0000-0012] ALU 6082 T6 plat 60x40 | __export__.product_product_14154_75692b32 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 8875 | 155
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 8875 | 7090
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 8875 | 790
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 8875 | 700
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 8875 | 140
TBRM Machining B.V. | Available | 2024-12-06 10:20 | __export__.mrp_production_1065_d70e7a5a | FALSE | 2025-03-19 14:39 | Normal | [7005-2480-0090] METROFRAME BODY V02-00-B / 0119073001 | 15889 | 4 | Pcs | TBRM /MO/00306 | S02403 | 2025-05-09 02:00 | 2025-05-30 02:00 | Confirmed | 2025-05-30 02:00 | [5601-0000-0155] ALU 5083 gegoten gzgd plaat 590x460x150 | __export__.product_product_16215_287d75f5 | 0 | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 4390 | 1530
[20 empty] | M5-04 - Haas - 5axis - Manual (UMC750SS) | __export__.mrp_workcenter_62_468a38e5 | FALSE | 4390 | 2860
TBRM Machining B.V. | Available | 2025-06-11 10:29 | __export__.mrp_production_4371_a96fc1a8 | FALSE | 2025-07-07 09:49 | Normal | [216121-0006] fixing block, actuator | 14910 | 10 | Pcs | TBRM /MO/00746 | S03183 | 2025-05-23 02:00 | 2025-07-11 02:00 | Confirmed | 2025-07-09 02:00 | [5602-0000-0037] RVS 304/304L wgw plat 25x20 | __export__.product_product_15116_26d7d7fd | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 125 | 25
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 125 | 90
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 125 | 10
TBRM Machining B.V. | Available | 2025-05-13 10:47 | __export__.mrp_production_4315_9685bbb0 | FALSE | 2025-11-21 16:04 | Normal | [4022-637-24142] HINGE BLOCK FIXED RF | 14961 | 44 | Pcs | TBRM /MO/00706 | S03084 | 2025-06-20 02:00 | 2025-07-11 02:00 | Confirmed | 2025-07-11 02:00 | [5602-0000-0003] RVS 304/304L wgw plat 40x30 | __export__.product_product_14170_ab4f36b5 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 2175 | 59
[20 empty] | M5-01 - Accuway - 5axis - Conveyor Automation (FR5_01) | __export__.mrp_workcenter_58_a525d5b9 | FALSE | 2175 | 1410
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 2175 | 530
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 2175 | 132
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 2175 | 44
TBRM Machining B.V. | Available | 2025-01-29 08:14 | __export__.mrp_production_1197_849443cd | TRUE | 2025-02-25 09:29 | Normal | [1082700B] Block cooling water TMP | 14907 | 68 | Pcs | TBRM /MO/00390 |  | 2025-07-17 14:51 | 2025-07-29 10:37 | Confirmed |  | [5602-0000-0024] RVS 316L wgw plat 40x25 | __export__.product_product_14191_eab5834c | 0 | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 3376 | 2538
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 3376 | 430
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 3376 | 340
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 3376 | 68
TBRM Machining B.V. | Available | 2025-06-11 10:29 | __export__.mrp_production_4370_ea015248 | TRUE | 2025-09-26 11:49 | Normal | [216121-0005] base wet stem quatro | 14908 | 49 | Pcs | TBRM /MO/00745 | S03183 | 2025-08-01 02:00 | 2025-09-19 02:00 | In Progress | 2025-07-09 02:00 | [5601-0000-0107] ALU 5754 H111 gzgd plaat 60x50x50 | __export__.product_product_15090_ae4a700a | 0 | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 11671 | 4500
[20 empty] | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 11671 | 0
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 11671 | 1315
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 11671 | 384
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 11671 | 286
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 11671 | 392
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 11671 | 4500
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 11671 | 245
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 11671 | 49
TBRM Machining B.V. | Not Available | 2025-09-03 11:59 | __export__.mrp_production_4841_95fde8df | FALSE | 2025-09-16 09:30 | Normal | [4522-980-37891] Filterplate al 5 | 15021 | 201 | Pcs | TBRM /MO/00951 | S03474 | 2025-08-28 02:00 | 2025-09-18 02:00 | Confirmed | 2025-09-18 11:00 | [5601-0000-0118] ALU 99.5 40HV UN-T136 plaat 145x145x6 | __export__.product_product_15101_5dce5b8d | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 2100 | 0
[20 empty] | M3-02 - Accuway - 3axis - Manual (FR3_02) | __export__.mrp_workcenter_55_15609e22 | FALSE | 2100 | 1698
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 2100 | 201
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 2100 | 201
TBRM Machining B.V. | Available | 2025-09-09 10:48 | __export__.mrp_production_4875_38ec7d1f | TRUE | 2025-10-28 11:52 | Normal | [4022.622.61092] RH RED GRIPPER CABLE COVER | 7366 | 34 | Pcs | TBRM /MO/00985 | S03487 | 2025-09-08 02:00 | 2026-01-07 12:34 | In Progress | 2025-11-03 01:00 | [5602-0000-0031] RVS 316L wgw plat 80x20 | __export__.product_product_14485_407ff3ad | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 13221 | 49
[20 empty] | M5-04 - Haas - 5axis - Manual (UMC750SS) | __export__.mrp_workcenter_62_468a38e5 | FALSE | 13221 | 740
[20 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | FALSE | 13221 | 1148
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 13221 | 2250
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 13221 | 2250
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 13221 | 6750
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 13221 | 34
TBRM Machining B.V. | Available | 2025-09-12 12:43 | __export__.mrp_production_4894_c0252ff7 | FALSE | 2025-11-18 10:53 | Normal | [00429-00-662-B] Arret lever | 14895 | 400 | Pcs | TBRM /MO/01000 | Manual Replenishment | 2025-09-12 02:00 | 2025-10-03 02:00 | Confirmed | 2025-10-03 12:43 | [5601-0000-0007] ALU 6082 T6 vk 30 | __export__.product_product_14149_55705e3a | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 7305 | 415
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 7305 | 5690
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 7305 | 800
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 7305 | 400
TBRM Machining B.V. | Available | 2025-10-21 15:00 | __export__.mrp_production_5031_9e2495e9 | FALSE | 2025-11-06 16:54 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 15022 | 87 | Pcs | TBRM /MO/01087 | S03493 | 2025-10-03 02:00 | 2025-11-21 01:00 | Confirmed | 2025-11-21 11:00 | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 12153 | 102
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 12153 | 2265
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 12153 | 438
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 12153 | 261
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 12153 | 9000
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 12153 | 87
TBRM Machining B.V. | Available | 2025-10-10 09:16 | __export__.mrp_production_4967_3148a862 | FALSE | 2025-10-10 09:16 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 15022 | 386 | Pcs | TBRM /MO/00878-002 |  | 2025-10-10 09:16 | 2025-11-28 08:16 | Confirmed |  | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 22319 | 401
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 22319 | 9740
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 22319 | 1634
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 22319 | 1158
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 22319 | 9000
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 22319 | 386
TBRM Machining B.V. | Available | 2025-10-08 12:50 | __export__.mrp_production_4956_ec0ffba5 | FALSE | 2025-10-28 13:21 | Normal | [100160036] EPSON-i3200_InksupplyUpperplate8Channel / SUSS | 18212 | 5 | Pcs | TBRM /MO/01036 | S03566 | 2025-10-22 02:00 | 2025-11-12 01:00 | Confirmed | 2025-11-12 01:00 | [5608-0000-0006] PEEK naturel gzgd plaat 465x150x10 / Victrex | __export__.product_product_18353_f07b016c | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 5 | 5
TBRM Machining B.V. | Available | 2025-11-21 13:58 | __export__.mrp_production_5207_49934e8f | FALSE | 2025-11-21 13:58 | Normal | [4022.632.63021] WTP LOCKING NUT | 7034 | 512 | Pcs | TBRM /MO/00879-005 | S03410 | 2025-10-23 02:00 | 2025-11-13 01:00 | Confirmed | 2025-11-13 01:00 | [5602-0000-0058] RVS 303 (1.4305) wgw geschild rond dia 40 | __export__.product_product_17313_9cdb5eb7 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 7499 | 527
[20 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | FALSE | 7499 | 6972
TBRM Machining B.V. | Available | 2025-10-15 11:36 | __export__.mrp_production_4994_50f61350 | FALSE | 2025-10-30 10:24 | Normal | [22203901] WSS alignment tool base V02-01 / NFI | 18304 | 3 | Pcs | TBRM /MO/01054 | S03591 | 2025-10-30 01:00 | 2025-11-20 01:00 | Confirmed | 2025-11-20 01:00 | [5601-0000-0204] ALU 6082 T651 (wgw) gzgd plaat 500x300x80 | __export__.product_product_18408_336c82d0 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 2253 | 3
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 2253 | 2250
TBRM Machining B.V. | Available | 2025-11-04 11:48 | __export__.mrp_production_5102_6bc4e277 | TRUE | 2025-11-27 14:37 | Normal | [00385-00-346-A] Plint fixing strip right | 14892 | 329 | Pcs | TBRM /MO/01104-001 | OP/14110 | 2025-11-04 01:00 | 2026-02-25 13:59 | In Progress | 2025-12-02 11:00 | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 7709 | 344
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 7709 | 2722
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 7709 | 1406
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 7709 | 658
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 7709 | 2250
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 7709 | 329
TBRM Machining B.V. | Available | 2025-11-04 12:04 | __export__.mrp_production_5103_54a89410 | FALSE | 2025-11-10 14:04 | Normal | [00385-00-102-C] Height bearing clamp plate | 14886 | 600 | Pcs | TBRM /MO/01105 | OP/14111 | 2025-11-04 01:00 | 2025-12-23 01:00 | Confirmed | 2025-12-23 11:00 | [5603-0000-0003] STAAL S355J2C+C ngl plat 50x20 | __export__.product_product_14198_828edea3 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 16995 | 615
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 16995 | 4890
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 16995 | 1890
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 16995 | 9000
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 16995 | 600
TBRM Machining B.V. | Available | 2025-11-27 14:37 | __export__.mrp_production_5253_f5d2d7d4 | TRUE | 2025-11-27 14:37 | Normal | [00385-00-346-A] Plint fixing strip right | 14892 | 356 | Pcs | TBRM /MO/01104-002 | OP/14110 | 2025-11-04 01:00 | 2025-12-02 01:00 | Confirmed | 2025-12-02 11:00 | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 8141 | 371
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 8141 | 2938
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 8141 | 1514
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 8141 | 712
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 8141 | 2250
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 8141 | 356
TBRM Machining B.V. | Available | 2025-11-05 17:03 | __export__.mrp_production_5109_96246a60 | FALSE | 2025-11-24 13:14 | Normal | [4022.689.94931] RH RED DP PT LOWER COVER | 17481 | 2 | Pcs | TBRM /MO/01108 | S03660 | 2025-11-06 01:00 | 2025-11-27 01:00 | Confirmed | 2025-11-27 01:00 | [5601-0000-0182] ALU 5083 (O3) gegoten 6z gezaagd plaat 570x350x50 | __export__.product_product_17605_d1ef1d9f | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 2888 | 120
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 2888 | 518
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 2888 | 2250
TBRM Machining B.V. | Available | 2025-11-05 17:03 | __export__.mrp_production_5110_924052ad | FALSE | 2025-11-17 15:56 | Normal | [4022.689.94981] RH RED DP PT UPPER COVER | 17484 | 2 | Pcs | TBRM /MO/01109 | S03660 | 2025-11-06 01:00 | 2025-11-27 01:00 | Confirmed | 2025-11-27 01:00 | [5601-0000-0181] ALU 5083 (O3) gegoten 6z gezaagd plaat 610x350x30 | __export__.product_product_17604_d75bd19d | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 2726 | 2
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 2726 | 474
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 2726 | 2250
TBRM Machining B.V. | Available | 2025-11-06 10:32 | __export__.mrp_production_5125_b56511f4 | FALSE | 2025-11-27 12:00 | Normal | [4022.693.44221] RH BACK PLATE ATM RTIPCA | 17465 | 15 | Pcs | TBRM /MO/01114 | S03662 | 2025-11-06 01:00 | 2025-11-27 01:00 | Confirmed | 2025-11-27 01:00 | [5601-0000-0051] ALU 5083 H111 (wgw) gzgd plaat 200x15 | __export__.product_product_14407_1cda6887 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 7650 | 30
[20 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | FALSE | 7650 | 3120
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 7650 | 4500
TBRM Machining B.V. | Available | 2025-11-06 10:32 | __export__.mrp_production_5126_a451a776 | FALSE | 2025-11-27 11:30 | Normal | [4022.693.44241] RH EMI SHIELD ATM RTIPCA | 17477 | 15 | Pcs | TBRM /MO/01115 | S03662 | 2025-11-06 01:00 | 2025-11-27 01:00 | Confirmed | 2025-11-27 01:00 | [5601-0000-0051] ALU 5083 H111 (wgw) gzgd plaat 200x15 | __export__.product_product_14407_1cda6887 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 7650 | 30
[20 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | FALSE | 7650 | 3120
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 7650 | 4500
TBRM Machining B.V. | Available | 2025-10-07 09:35 | __export__.mrp_production_4938_ea5c2f00 | TRUE | 2025-11-17 15:56 | Normal | [4022.623.82781] RH EMI SHIELD VAC RTIPCA | 17459 | 16 | Pcs | TBRM /MO/01025 | S03560 | 2025-11-07 01:00 | 2026-02-04 09:30 | In Progress | 2025-11-28 01:00 | [5601-0000-0051] ALU 5083 H111 (wgw) gzgd plaat 200x15 | __export__.product_product_14407_1cda6887 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 9811 | 31
[20 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | FALSE | 9811 | 780
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 9811 | 4500
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 9811 | 4500
TBRM Machining B.V. | Available | 2025-11-06 15:28 | __export__.mrp_production_5128_5077dbf0 | FALSE | 2025-11-21 13:19 | Normal | [7001-2540-0010] 12i Shield Mounting Block / FM / FM7031-M00033-B | 18475 | 4 | Pcs | TBRM /MO/01117 | S03671 | 2025-11-07 01:00 | 2025-11-28 01:00 | Confirmed | 2025-11-28 01:00 | [5602-0000-0073] RVS 304/304L gzgd plaat 200x100x20 | __export__.product_product_18569_1917b1b9 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 19 | 19
TBRM Machining B.V. | Available | 2025-11-10 09:38 | __export__.mrp_production_5132_8a506e23 | FALSE | 2025-11-26 08:33 | Normal | [E06581] 4598-013-97781 WA2 VIBRATION PAD LEFT SPACER blauw | 17519 | 400 | Pcs | TBRM /MO/01120 | S03678 | 2025-11-11 01:00 | 2025-12-02 01:00 | Confirmed | 2025-12-02 01:00 | [5601-0000-0183] ALU 6082 T651 (wgw) gzgd plaat 142x142x20 | __export__.product_product_17606_b972fa2d | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 2090 | 400
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 2090 | 1690
TBRM Machining B.V. |  | 2025-11-13 09:59 | __export__.mrp_production_5142_ccd39fd4 | FALSE | 2025-11-13 10:20 | Normal | flowteq koker | 18500 | 30 | Pcs | TBRM /MO/01128 | S03697 | 2025-11-13 | 2025-11-13 01:00 | Draft | 2025-11-20 01:00
TBRM Machining B.V. | Available | 2025-10-16 09:48 | __export__.mrp_production_5015_cdd78c28 | FALSE | 2025-10-24 14:45 | Normal | [4022-656-73531] Pipe clamp exhaust FW 1980 | 14976 | 86 | Pcs | TBRM /MO/01075 | OP/14069 - S03600 | 2025-11-13 01:00 | 2025-12-04 01:00 | Confirmed | 2025-12-04 01:00 | [5602-0000-0013] RVS 304/304L blank plat 50x8 | __export__.product_product_14180_b574d432 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 793 | 101
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 793 | 434
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 793 | 172
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 793 | 86
TBRM Machining B.V. | Available | 2025-11-06 10:20 | __export__.mrp_production_5124_b236bc43 | TRUE | 2025-11-12 10:43 | Normal | [4022-635-87291] HANDLE | 14958 | 75 | Pcs | TBRM /MO/01113 | S03666 | 2025-11-13 01:00 | 2025-11-14 13:45 | Confirmed | 2025-12-04 01:00 | [5602-0000-0001] RVS 304/304L blank plat 25x12 | __export__.product_product_14168_8e5a951b | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 1095 | 90
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 1095 | 690
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 1095 | 165
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 1095 | 75
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 1095 | 75
TBRM Machining B.V. | Not Available | 2025-10-16 09:45 | __export__.mrp_production_5014_625c3749 | FALSE | 2025-10-20 16:02 | Normal | [4022-631-99701] LCW ABS PRES SENS CONN BLOCK | 14954 | 130 | Pcs | TBRM /MO/01074 | OP/14058 - S03598 | 2025-11-14 01:00 | 2025-12-05 01:00 | Confirmed | 2025-12-05 01:00 | [5602-0000-0011] RVS 304/304L wgw vk 50 | __export__.product_product_14178_606b24aa | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 6695 | 145
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 6695 | 5030
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 6695 | 740
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 6695 | 650
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 6695 | 130
TBRM Machining B.V. | Available | 2025-10-16 11:10 | __export__.mrp_production_5019_630e7c08 | FALSE | 2025-10-22 11:30 | Normal | [M0216-01-091-A] Bev. Klitteband | 15041 | 2000 | Pcs | TBRM /MO/01079 | OP/14124 - S03606 | 2025-11-18 01:00 | 2025-12-09 01:00 | Confirmed | 2025-12-09 01:00 | [5601-0000-0111] ALU 6060 T66 plat 30x5 | __export__.product_product_15094_490f9528 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 8120 | 2015
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 8120 | 90
[20 empty] | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 8120 | 2015
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 8120 | 2000
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 8120 | 2000
TBRM Machining B.V. | Available | 2025-11-18 10:01 | __export__.mrp_production_5153_7c842e39 | FALSE | 2025-11-27 13:57 | Normal | [00385-00-274-D] Filling block | 14888 | 356 | Pcs | TBRM /MO/01138 | OP/14112 | 2025-11-18 01:00 | 2025-12-09 01:00 | Confirmed | 2025-12-09 11:00 | [5601-0000-0010] ALU 6082 T6 vk 70 | __export__.product_product_14152_7df8680e | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 5179 | 371
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 5179 | 2938
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 5179 | 1158
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 5179 | 356
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 5179 | 356
TBRM Machining B.V. | Available | 2025-11-18 10:01 | __export__.mrp_production_5154_8c51c3b6 | TRUE | 2025-11-26 10:46 | Normal | [00385-00-321-A] Plint fixing strip left | 14890 | 200 | Pcs | TBRM /MO/01139-001 | OP/14109 | 2025-11-18 01:00 | 2026-01-21 14:20 | In Progress | 2025-12-16 11:00 | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 5645 | 215
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 5645 | 1690
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 5645 | 890
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 5645 | 400
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 5645 | 2250
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 5645 | 200
TBRM Machining B.V. | Available | 2025-11-20 13:43 | __export__.mrp_production_5198_1e51f1d6 | FALSE | 2025-11-28 13:13 | Normal | [00385-00-329-A] End plate finger safety hinge | 14891 | 473 | Pcs | TBRM /MO/01162 | OP/14118 - S03745 | 2025-11-18 01:00 | 2025-12-16 01:00 | Confirmed | 2025-12-16 01:00 | [5603-0000-0006] STAAL S235JRC+C blank plat 20x5 | __export__.product_product_14201_02d1168d | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 5193 | 488
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 5193 | 1509
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 5193 | 473
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 5193 | 2250
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 5193 | 473
TBRM Machining B.V. | Available | 2025-11-25 09:37 | __export__.mrp_production_5212_13faa832 | TRUE | 2025-11-27 14:36 | Normal | [00385-00-321-A] Plint fixing strip left | 14890 | 153 | Pcs | TBRM /MO/01139-002 | OP/14109 | 2025-11-18 01:00 | 2026-02-11 11:33 | In Progress | 2025-12-16 11:00 | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 4893 | 168
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 4893 | 1314
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 4893 | 702
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 4893 | 306
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 4893 | 2250
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 4893 | 153
TBRM Machining B.V. | Available | 2025-11-27 14:36 | __export__.mrp_production_5252_9768dc48 | TRUE | 2025-11-27 14:36 | Normal | [00385-00-321-A] Plint fixing strip left | 14890 | 337 | Pcs | TBRM /MO/01139-003 | OP/14109 | 2025-11-18 01:00 | 2025-12-16 01:00 | Confirmed | 2025-12-16 11:00 | [5603-0000-0004] STAAL S235JRC+C blank plat 30x20 | __export__.product_product_14199_79840166 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 7837 | 352
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 7837 | 2786
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 7837 | 1438
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 7837 | 674
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 7837 | 2250
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 7837 | 337
TBRM Machining B.V. | Available | 2025-11-19 14:12 | __export__.mrp_production_5191_57caf28e | FALSE | 2025-11-28 13:13 | Normal | [00429-00-662-B] Arret lever | 14895 | 400 | Pcs | TBRM /MO/01155 | Manual Replenishment | 2025-11-19 01:00 | 2025-12-10 01:00 | Confirmed | 2025-12-10 14:11 | [5601-0000-0007] ALU 6082 T6 vk 30 | __export__.product_product_14149_55705e3a | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 7305 | 415
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 7305 | 5690
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 7305 | 800
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 7305 | 400
TBRM Machining B.V. | Available | 2025-11-14 12:12 | __export__.mrp_production_5146_15453986 | FALSE | 2025-11-14 12:12 | Normal | [000750458] Mounting Block for Flight | 17087 | 64 | Pcs | TBRM /MO/01132 | S03708 | 2025-11-20 01:00 | 2025-12-11 01:00 | Confirmed | 2025-12-11 01:00 | [5602-0000-0064] RVS 304/304L wgw vk 35 | __export__.product_product_17624_73707cca | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 1355 | 79
[20 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | FALSE | 1355 | 1276
TBRM Machining B.V. | Available | 2025-11-19 16:55 | __export__.mrp_production_5193_bb240b35 | FALSE | 2025-11-19 16:55 | Normal | [7005-2580-0017] GP Z-Adjustment Lever V02-01 / 26241001 | 18142 | 12 | Pcs | TBRM /MO/01157 | S03733 | 2025-11-20 01:00 | 2025-12-11 01:00 | Confirmed | 2025-12-11 01:00 | [5602-0000-0051] RVS 304/304L wgw plat 90x20 | __export__.product_product_16616_0f026687 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 3717 | 27
[20 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | FALSE | 3717 | 1440
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 3717 | 2250
TBRM Machining B.V. | Available | 2025-11-19 16:55 | __export__.mrp_production_5194_22067218 | FALSE | 2025-11-19 16:55 | Normal | [7005-2580-0005] Single Rail V01-00-A / IGUS / WSQ-06S | 16257 | 15 | Pcs | TBRM /MO/01158 | S03733 | 2025-11-20 01:00 | 2025-12-11 01:00 | Confirmed | 2025-12-11 01:00 | Single rail WSQ - not drilled / IGUS / WSQ-06S | __export__.product_product_16262_062fd235 | 0 | MP2 - Material preparation - manual sawing (ZGN_02) | __export__.mrp_workcenter_64_95992ef5 | FALSE | 165 | 15
[20 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | FALSE | 165 | 150
TBRM Machining B.V. | Available | 2025-10-16 09:50 | __export__.mrp_production_5016_d46c7b38 | FALSE | 2025-10-16 14:01 | Normal | [4022-335-71012] filter holder | 14923 | 40 | Pcs | TBRM /MO/01076 | S03602 | 2025-11-21 01:00 | 2025-12-12 01:00 | Confirmed | 2025-12-12 01:00 | [5604-0000-0004] MESSING CuZn40Pb2 plat 20x10 | __export__.product_product_14167_a3f963d3 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 675 | 55
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 675 | 330
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 675 | 170
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 675 | 80
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 675 | 40
TBRM Machining B.V. | Available | 2025-11-19 16:55 | __export__.mrp_production_5192_879adede | FALSE | 2025-11-24 10:05 | Normal | [7005-2580-0015] Baseplate V01-00 / NFI / 27244702 | 17993 | 5 | Pcs | TBRM /MO/01156 | S03733 | 2025-11-21 01:00 | 2025-12-12 01:00 | In Progress | 2025-12-12 01:00 | [5601-0000-0175] ALU 5083 gegoten 6 zijdig gezaagd 520x250x45 | __export__.product_product_17008_b36cccae | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 3040 | 5
[20 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | FALSE | 3040 | 785
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 3040 | 2250
TBRM Machining B.V. | Available | 2025-11-11 13:46 | __export__.mrp_production_5135_fb4139a8 | FALSE | 2025-11-26 10:43 | Normal | [7007-2500-0005] TL 1 - Feet Dark / IAH / 105886 | 18484 | 6 | Pcs | TBRM /MO/01123 | S03682 | 2025-11-24 01:00 | 2025-12-15 01:00 | Confirmed | 2025-12-15 01:00 | [5601-0000-0180] ALU 5083 H111 (wgw) gzgd plaat 310x282x35 | __export__.product_product_17403_35732fb0 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 5268 | 6
[20 empty] | M3-03 - Haas - 3axis - Manual (VF2SS) | __export__.mrp_workcenter_60_6593b576 | FALSE | 5268 | 762
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 5268 | 4500
TBRM Machining B.V. | Available | 2025-11-28 13:17 | __export__.mrp_production_5255_92200c6a | FALSE | 2025-11-28 13:17 | Normal | [4022.704.19282] RH RED GRIPPER BODY | 14210 | 29 | Pcs | TBRM /MO/01080-002 | S03610 | 2025-11-24 01:00 | 2025-12-15 01:00 | Confirmed | 2025-12-15 01:00 | [5602-0000-0060] RVS 316/316L gzgd plaat 210x105x30 (tol. -0/+3mm) | __export__.product_product_17381_95528666 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 16259 | 29
[20 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | FALSE | 16259 | 13980
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 16259 | 2250
TBRM Machining B.V. | Not Available | 2025-11-25 17:03 | __export__.mrp_production_5213_0247fdca | FALSE | 2025-11-25 17:03 | Normal | [00429-00-249-A] Plint adjust strip | 14894 | 436 | Pcs | TBRM /MO/01174 | OP/14115 | 2025-11-25 01:00 | 2025-12-23 01:00 | Confirmed | 2025-12-23 11:00 | [5603-0000-0013] S235JRC+C blank plat 40x10 (ca 3-3,5 mtr) | __export__.product_product_15106_3345092e | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 6279 | 451
[20 empty] | M4-01 - Accuway - 4axis - Conveyor Automation (FR4_01) | __export__.mrp_workcenter_56_d6637dea | FALSE | 6279 | 2706
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 6279 | 436
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 6279 | 2250
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 6279 | 436
TBRM Machining B.V. | Available | 2025-11-06 09:28 | __export__.mrp_production_5123_34859f5a | FALSE | 2025-11-06 14:10 | Normal | [4022-456-08803] LENSGAS INTERFACE BLOCK | 14932 | 15 | Pcs | TBRM /MO/01112 | S03664 | 2025-11-26 01:00 | 2025-12-17 01:00 | Confirmed | 2025-12-17 01:00 | [5602-0000-0041] RVS 430F blank rond 50h9 | __export__.product_product_15120_10aecd71 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 720 | 30
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 720 | 105
[20 empty] | M5-01 - Accuway - 5axis - Conveyor Automation (FR5_01) | __export__.mrp_workcenter_58_a525d5b9 | FALSE | 720 | 390
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 720 | 165
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 720 | 15
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 720 | 15
TBRM Machining B.V. | Available | 2025-11-27 15:02 | __export__.mrp_production_5254_a5ca04b7 | FALSE | 2025-11-27 15:02 | Normal | [100161448] Modified part of Enclose extrud alu_145 / SUSS / HAMMOND-1457U2801 | 18558 | 5 | Pcs | TBRM /MO/01183 | Manual Replenishment | 2025-11-27 14:02 | 2025-11-27 15:02 | Confirmed | 2025-11-27 14:02
TBRM Machining B.V. |  | 2025-10-21 16:13 | __export__.mrp_production_5033_ffa23c2e | FALSE | 2025-10-21 16:13 | Normal | [4022.684.28993] RS C+H SLAB STAT PLT IL SIDE / CLS | 18261 | 1 | Pcs | TBRM /MO/01089 | S03624 | 2025-11-28 | 2025-11-28 01:00 | Draft | 2025-11-28 01:00
TBRM Machining B.V. |  | 2025-10-21 16:13 | __export__.mrp_production_5034_4d53b4c4 | FALSE | 2025-10-21 16:13 | Normal | [4022.684.29043] RS C+H DYN ATTACH PLT IL SIDE / CLS | 18342 | 1 | Pcs | TBRM /MO/01090 | S03624 | 2025-11-28 | 2025-11-28 01:00 | Draft | 2025-11-28 01:00
TBRM Machining B.V. |  | 2025-10-21 16:13 | __export__.mrp_production_5035_e3dce293 | FALSE | 2025-10-21 16:13 | Normal | [4022.684.28962] RS C+H DYN ATTACH PLT RH SIDE / CLS | 18348 | 1 | Pcs | TBRM /MO/01091 | S03624 | 2025-11-28 | 2025-11-28 01:00 | Draft | 2025-11-28 01:00
TBRM Machining B.V. |  | 2025-10-21 16:13 | __export__.mrp_production_5036_bec2ca68 | FALSE | 2025-10-21 16:13 | Normal | [4022.684.28842] RS C+H SLAB STAT PLT RH SIDE / CLS | 18349 | 1 | Pcs | TBRM /MO/01092 | S03624 | 2025-11-28 | 2025-11-28 01:00 | Draft | 2025-11-28 01:00
TBRM Machining B.V. |  | 2025-10-21 16:13 | __export__.mrp_production_5037_60eed60d | FALSE | 2025-10-21 16:13 | Normal | [4022.656.37971] UXL2 DGF QCK CONNECT MANIFOLD / CLS | 18350 | 5 | Pcs | TBRM /MO/01093 | S03624 | 2025-11-28 | 2025-11-28 01:00 | Draft | 2025-11-28 01:00
TBRM Machining B.V. | Available | 2025-11-07 10:55 | __export__.mrp_production_5131_a5c1b71e | FALSE | 2025-11-10 09:34 | Normal | [4022.622.61941] RH RED FRAME -X COVER | 16115 | 1 | Pcs | TBRM /MO/01119 | S03677 | 2025-12-01 01:00 | 2025-12-22 01:00 | Confirmed | 2025-12-22 01:00 | [5601-0000-0161] ALU 6082 T651 (wgw) gzgd plaat 500x365x100 | __export__.product_product_16323_9b13f8a6 | 0 | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 8853 | 1290
[20 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | FALSE | 8853 | 813
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 8853 | 2250
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 8853 | 4500
TBRM Machining B.V. |  | 2025-11-20 11:23 | __export__.mrp_production_5197_add2b8a9 | FALSE | 2025-11-20 11:23 | Normal | [Z5191180] Z5191180 | 18592 | 75 | Pcs | TBRM /MO/01161 | S03742 | 2025-12-08 | 2025-12-08 01:00 | Draft | 2025-12-08 01:00
TBRM Machining B.V. |  | 2025-11-11 11:40 | __export__.mrp_production_5133_b9bdcd5e | FALSE | 2025-11-11 11:40 | Normal | [Z4611960] Z4611960 | 18481 | 1400 | Pcs | TBRM /MO/01121 | S03680 | 2025-12-12 | 2025-12-12 01:00 | Draft | 2025-12-12 01:00
TBRM Machining B.V. |  | 2025-11-11 11:40 | __export__.mrp_production_5134_0ea674be | FALSE | 2025-11-11 11:40 | Normal | [Z4610530] Z4610530 | 18482 | 1400 | Pcs | TBRM /MO/01122 | S03680 | 2025-12-12 | 2025-12-12 01:00 | Draft | 2025-12-12 01:00
TBRM Machining B.V. | Exp 02/12/2025 | 2025-11-18 10:01 | __export__.mrp_production_5152_da0fa32e | FALSE | 2025-11-18 13:54 | Normal | [4022-666-3837-1] LSPH Bellow Clamp | 14985 | 200 | Pcs | TBRM /MO/01137 | S03717 | 2025-12-12 01:00 | 2026-01-09 01:00 | Confirmed | 2026-01-09 01:00 | [5990-0000-0017] LSPH Bellow Clamp cutout | __export__.product_product_15112_c44437c2 | 0 | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 2380 | 1090
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 2380 | 690
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 2380 | 400
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 2380 | 200
TBRM Machining B.V. | Not Available | 2025-11-27 10:27 | __export__.mrp_production_5233_e8375207 | FALSE | 2025-11-27 10:27 | Normal | [4598-008-08901B POS 1] CEILING INLET* | 15022 | 300 | Pcs | TBRM /MO/01176 | S03764 | 2025-12-12 01:00 | 2026-01-30 01:00 | Confirmed | 2026-01-30 01:00 | [5990-0000-0013] EPRAFORM PC helder rond Ø125 | __export__.product_product_15108_e3fe93a6 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 19395 | 315
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 19395 | 7590
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 19395 | 1290
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 19395 | 900
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 19395 | 9000
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 19395 | 300
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5156_89ad707f | FALSE | 2025-11-18 11:41 | Normal | [FM3001-M00050] SPG PG Top Plate / FM / FM3001-M00050 | 18572 | 1 | Pcs | TBRM /MO/01141 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5157_c42ee97f | FALSE | 2025-11-18 11:41 | Normal | [FM3001-M00051] SPS PG Bottom Plate / FM / FM3001-M00051 | 18573 | 1 | Pcs | TBRM /MO/01142 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5158_7a489b00 | FALSE | 2025-11-18 11:41 | Normal | [FM3001-M00055] SPG PG Pancake Ejector Ring / FM / FM3001-M00055 | 18574 | 1 | Pcs | TBRM /MO/01143 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5159_3c33ca56 | FALSE | 2025-11-18 11:46 | Normal | [FM3001-M00057] SPG SE Side Plate / FM / FM3001-M00057 | 18575 | 2 | Pcs | TBRM /MO/01144 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5160_0d19a309 | FALSE | 2025-11-18 11:41 | Normal | [FM3001-M00059] SPS SE Intermediate Joint / FM / FM3001-M00059 | 18576 | 1 | Pcs | TBRM /MO/01145 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5161_2e80390a | FALSE | 2025-11-18 11:41 | Normal | [FM3001-M00061] SPS SE Guide Block / FM / FM3001-M00061 | 18577 | 1 | Pcs | TBRM /MO/01146 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5162_ef98c835 | FALSE | 2025-11-18 11:41 | Normal | [FM3001-M00062] SPS SE Pivotting Arm / FM / FM3001-M00062 | 18578 | 1 | Pcs | TBRM /MO/01147 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. |  | 2025-11-18 11:41 | __export__.mrp_production_5163_ce692cf6 | FALSE | 2025-11-18 11:41 | Normal | [FM3001-M00063] SPS SE Ejector Joint / FM / FM3001-M00063 | 18579 | 1 | Pcs | TBRM /MO/01148 | S03718 | 2025-12-15 | 2025-12-15 01:00 | Draft | 2025-12-15 01:00
TBRM Machining B.V. | Available | 2025-11-06 14:02 | __export__.mrp_production_5127_c4b6d523 | FALSE | 2025-11-21 12:52 | Normal | [4022.632.63021] WTP LOCKING NUT | 7034 | 1800 | Pcs | TBRM /MO/01116 | S03669 | 2025-12-15 01:00 | 2026-01-05 01:00 | Confirmed | 2026-01-05 01:00 | [5602-0000-0058] RVS 303 (1.4305) wgw geschild rond dia 40 | __export__.product_product_17313_9cdb5eb7 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 26175 | 1815
[20 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | FALSE | 26175 | 24360
TBRM Machining B.V. | Available | 2025-11-13 08:56 | __export__.mrp_production_5139_6ec4ad82 | FALSE | 2025-11-27 07:59 | Normal | [4022-637-68442] IH HINGE BRACKET TOP HINGE | 14969 | 110 | Pcs | TBRM /MO/01125 | OP/14067 - S03691 | 2025-12-15 01:00 | 2026-01-05 01:00 | Confirmed | 2026-01-05 01:00 | [5603-0000-0011] STAAL S355J2C+C ngl plat 60x40 | __export__.product_product_14206_bee047c5 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 1845 | 125
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 1845 | 970
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 1845 | 420
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 1845 | 220
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 1845 | 110
TBRM Machining B.V. |  | 2025-11-18 12:26 | __export__.mrp_production_5167_29e67655 | FALSE | 2025-11-18 12:26 | Normal | [4022-637-44661] Hinge block 7c-e rr | 15576 | 7 | Pcs | TBRM /MO/01151 | S03722 | 2025-12-17 | 2025-12-17 01:00 | Draft | 2025-12-17 01:00
TBRM Machining B.V. |  | 2025-11-27 10:40 | __export__.mrp_production_5238_8767ee54 | FALSE | 2025-11-27 10:40 | Normal | [4022-631-06691] Hinge Block Front rm2 | 16312 | 1 | Pcs | TBRM /MO/01181 | S03772 | 2025-12-17 | 2025-12-17 01:00 | Draft | 2025-12-17 01:00
TBRM Machining B.V. | Exp 27/11/2025 | 2025-11-18 12:17 | __export__.mrp_production_5166_fc264293 | FALSE | 2025-11-18 12:17 | Normal | [4022-333-19505] BRIL | 14918 | 100 | Pcs | TBRM /MO/01150 | OP/14048 - S03720 | 2025-12-18 01:00 | 2026-01-08 01:00 | Confirmed | 2026-01-08 01:00 | [5990-0000-0014] EPRATEX PF CC201 180x140x10 | __export__.product_product_15109_d51d8015 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 1490 | 0
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 1490 | 1090
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 1490 | 300
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 1490 | 100
TBRM Machining B.V. | Available | 2025-11-18 12:33 | __export__.mrp_production_5168_bf7bb95a | FALSE | 2025-11-28 13:13 | Normal | [4022-637-24142] HINGE BLOCK FIXED RF | 14961 | 26 | Pcs | TBRM /MO/01152 | S03724 | 2025-12-18 01:00 | 2026-01-08 01:00 | Confirmed | 2026-01-08 01:00 | [5602-0000-0003] RVS 304/304L wgw plat 40x30 | __export__.product_product_14170_ab4f36b5 | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 1365 | 41
[20 empty] | M5-01 - Accuway - 5axis - Conveyor Automation (FR5_01) | __export__.mrp_workcenter_58_a525d5b9 | FALSE | 1365 | 870
[20 empty] | M4-02 - Accuway - 4axis - Conveyor Automation (FR4_02) | __export__.mrp_workcenter_57_6faf5319 | FALSE | 1365 | 350
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 1365 | 78
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 1365 | 26
TBRM Machining B.V. | Available | 2025-11-18 12:35 | __export__.mrp_production_5169_605d6f4a | FALSE | 2025-11-25 09:00 | Normal | [4022-637-24191] HINGE BLOCK RF | 14962 | 47 | Pcs | TBRM /MO/01153 | OP/14063 - S03726 | 2025-12-18 01:00 | 2026-01-08 01:00 | Confirmed | 2026-01-08 01:00 | [5602-0000-0009] RVS 304/304L wgw plat 100x20 | __export__.product_product_14176_d2113b2d | 0 | MP1 - Material preparation - automatic sawing (ZGN_01) | __export__.mrp_workcenter_63_98a7a00b | FALSE | 1840 | 62
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 1840 | 1265
[20 empty] | M5-02 - Accuway - 5axis - Pallet Automation (FR5_02) | __export__.mrp_workcenter_59_d6deab7b | FALSE | 1840 | 372
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 1840 | 94
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 1840 | 47
TBRM Machining B.V. | Exp 27/11/2025 | 2025-11-18 13:17 | __export__.mrp_production_5170_e417b5e3 | FALSE | 2025-11-18 13:17 | Normal | [4022-333-19505] BRIL | 14918 | 100 | Pcs | TBRM /MO/01154 | OP/14048 - S03728 | 2025-12-18 01:00 | 2026-01-08 01:00 | Confirmed | 2026-01-08 01:00 | [5990-0000-0014] EPRATEX PF CC201 180x140x10 | __export__.product_product_15109_d51d8015 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 1490 | 0
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 1490 | 1090
[20 empty] | BW - Benchwork (BKW_01) | __export__.mrp_workcenter_66_9f807a30 | FALSE | 1490 | 300
[20 empty] | PACK - Packaging (VERP_P) | __export__.mrp_workcenter_67_d1ac8ce6 | FALSE | 1490 | 100
TBRM Machining B.V. |  | 2025-11-20 13:55 | __export__.mrp_production_5200_79500479 | FALSE | 2025-11-20 13:55 | Normal | [DW-00-001] Battery cover / DW | 18600 | 1 | Pcs | TBRM /MO/01164 | S03746 | 2025-12-19 | 2025-12-19 01:00 | Draft | 2025-12-19 01:00
TBRM Machining B.V. |  | 2025-11-20 13:55 | __export__.mrp_production_5201_363c6277 | FALSE | 2025-11-20 13:55 | Normal | [DW-00-002] Nose cover - DW | 18601 | 1 | Pcs | TBRM /MO/01165 | S03746 | 2025-12-19 | 2025-12-19 01:00 | Draft | 2025-12-19 01:00
TBRM Machining B.V. |  | 2025-11-20 13:55 | __export__.mrp_production_5202_397a768d | FALSE | 2025-11-20 13:55 | Normal | [DW-00-003] Parachute Cover - DW | 18602 | 1 | Pcs | TBRM /MO/01166 | S03746 | 2025-12-19 | 2025-12-19 01:00 | Draft | 2025-12-19 01:00
TBRM Machining B.V. |  | 2025-11-20 13:55 | __export__.mrp_production_5203_a08f58a0 | FALSE | 2025-11-20 13:55 | Normal | [DW-00-006-001] DW-00-006-001 / DW | 18603 | 1 | Pcs | TBRM /MO/01167 | S03746 | 2025-12-19 | 2025-12-19 01:00 | Draft | 2025-12-19 01:00
TBRM Machining B.V. |  | 2025-11-20 13:55 | __export__.mrp_production_5204_63e7eaf6 | FALSE | 2025-11-20 13:55 | Normal | [DW-00-006-002] DW-00-006-002 / DW | 18604 | 1 | Pcs | TBRM /MO/01168 | S03746 | 2025-12-19 | 2025-12-19 01:00 | Draft | 2025-12-19 01:00
TBRM Machining B.V. |  | 2025-11-20 13:55 | __export__.mrp_production_5205_3d2f0ba8 | FALSE | 2025-11-20 13:55 | Normal | [DW-00-007-001] DW-00-007-001 / DW | 18605 | 1 | Pcs | TBRM /MO/01169 | S03746 | 2025-12-19 | 2025-12-19 01:00 | Draft | 2025-12-19 01:00
TBRM Machining B.V. |  | 2025-11-20 13:55 | __export__.mrp_production_5206_d453b650 | FALSE | 2025-11-20 13:55 | Normal | [DW-00-007-002] DW-00-007-002 / DW | 18606 | 1 | Pcs | TBRM /MO/01170 | S03746 | 2025-12-19 | 2025-12-19 01:00 | Draft | 2025-12-19 01:00
TBRM Machining B.V. | Exp 28/11/2025 | 2025-11-21 15:51 | __export__.mrp_production_5211_e60f1304 | FALSE | 2025-11-21 15:51 | Normal | [4022.706.05882] EXE IL IXF MOD TA GUIDE / HQP | 18078 | 4 | Pcs | TBRM /MO/01173 | S03753 | 2025-12-19 01:00 | 2026-01-09 01:00 | Confirmed | 2026-01-09 01:00 | [5601-0000-0203] ALU 5083 H111 (wgw) gzgd plaat 645x75x50 | __export__.product_product_18250_19c78435 | 0 | MP3 - Material preparation - pre-cutted, only picking (UITG_M) | __export__.mrp_workcenter_65_c1e1b939 | FALSE | 5398 | 4
[20 empty] | M3-01 - Accuway - 3axis - Manual (FR3_01) | __export__.mrp_workcenter_54_3f0243e1 | FALSE | 5398 | 706
[20 empty] | M5-03 - Haas - 5axis - Manual (UMC750) | __export__.mrp_workcenter_61_bcb50df3 | FALSE | 5398 | 188
[20 empty] | OUT - Outsourced activity | __export__.mrp_workcenter_68_8bff6631 | FALSE | 5398 | 4500
TBRM Machining B.V. |  | 2025-11-17 10:57 | __export__.mrp_production_5148_cddb4063 | FALSE | 2025-11-17 10:57 | Normal | [4022.719.28491] HALFFAB M PLATE SST 150x40x15 / HQP / 104018451 | 18565 | 4 | Pcs | TBRM /MO/01133 | S03710 | 2025-12-22 | 2025-12-22 01:00 | Draft | 2025-12-22 01:00
TBRM Machining B.V. |  | 2025-11-17 10:57 | __export__.mrp_production_5149_79afd335 | FALSE | 2025-11-17 10:57 | Normal | [4022.719.44971] HALFFAB M CL SP SST 150x30x159 / HQP / 104018452 | 18566 | 2 | Pcs | TBRM /MO/01134 | S03710 | 2025-12-22 | 2025-12-22 01:00 | Draft | 2025-12-22 01:00